## Delay Register
S.N | Activity | Baseline Finish | Anticipated / Actual finish as per current progress | Delay (days) | Type of Delay | Status | Remarks | Report No | Date
1 | Main building - Steel Structure & Decking sheets - Delivery | 2021-09-02 | 2021-09-30 | 29 | Critical | Ongoing | 92% of structural steel and 87% of decking sheets were delivered at site | 19 | 2021-09-24
2 | Main building - Steel Structure erection | 2021-09-11 | 2021-10-09 | 29 | Critical | Ongoing | Delayed due to lack of resources | 19 | 2021-09-24
3 | Main building - Deck sheets fixing | 2021-09-15 | 2021-10-15 | 31 | Critical | Ongoing | Delayed due to steel structure erection | 19 | 2021-09-24
4 | Main building - Deck slab concrete - Terrace floor | 2021-09-29 | 2021-10-25 | 27 | Critical | Not Started | Delayed due to deck sheets erection & lack of resources | 19 | 2021-09-24
5 | Main building - Deck slab concrete - 4th floor | 2021-09-20 | 2021-11-10 | 52 | Critical | Not Started | Delayed due to deck sheets erection & lack of resources | 19 | 2021-09-24
6 | Main building - Blockwork at Ground floor | 2021-09-01 | 2021-09-30 | 30 | Critical | Ongoing | Delayed due to grade slab concreting & lack of resources | 19 | 2021-09-24
7 | Main building - Blockwork at 1st floor | 2021-08-26 | 2021-10-08 | 44 | Critical | Ongoing | Delayed due to deck slab concreting | 19 | 2021-09-24
8 | Main building - Blockwork at 2nd floor | 2021-08-16 | 2021-10-15 | 61 | Critical | Ongoing | Delayed due to deck slab concreting | 19 | 2021-09-24
9 | Main building - MEP 1st fix - ceiling at GF | 2021-10-05 | 2021-10-30 | 26 | Critical | Ongoing | Delayed due to 1st floor deck slab | 19 | 2021-09-24
10 | Main building - MEP 1st fix - ceiling at 1st floor | 2021-10-13 | 2021-11-05 | 24 | Critical | Ongoing | Delayed due to 2nd floor deck slab | 19 | 2021-09-24
11 | Main building - Partition walls 1st fix at GF | 2021-09-07 | 2021-10-10 | 34 | Critical | Ongoing | Delayed due to blockworks | 19 | 2021-09-24
12 | Main building - Plastering at GF | 2021-09-22 | 2021-10-06 | 15 | Critical | Ongoing | Delayed due to MEP 1st fix | 19 | 2021-09-24
13 | Main building - Plastering at 1st floor | 2021-09-08 | 2021-10-14 | 37 | Critical | Ongoing | Delayed due to MEP 1st fix | 19 | 2021-09-24
14 | Main building - Partition walls 1st fix at 1st floor | 2021-09-20 | 2021-10-17 | 28 | Critical | Ongoing | Delayed due to blockworks | 19 | 2021-09-24
15 | DG Building - steel erection | 2021-09-09 | 2021-10-26 | 48 | Noncritical | Not Started | Materials yet to be received | 19 | 2021-09-24
16 | DG Building - Deck sheet fixing | 2021-09-11 | 2021-10-28 | 48 | Noncritical | Not Started | Materials yet to be received | 19 | 2021-09-24
17 | Substation building - Superstructure works | 2021-09-13 | 2021-10-08 | 26 | Critical | Ongoing | Delayed due to substructure works | 19 | 2021-09-24
18 | Transformer - Trench works | 2021-09-20 | 2021-12-16 | 88 | Noncritical | Ongoing | Delayed due to workspace | 19 | 2021-09-24
19 | Road works - Phase 1 | 2021-12-17 | 2022-02-01 | 47 | Noncritical | Ongoing |  | 19 | 2021-09-24
20 | Road works - Phase 2 | 2021-11-30 | 2022-02-01 | 64 | Noncritical | Ongoing |  | 19 | 2021-09-24
1 | Main building - Steel Structure erection | 2021-09-11 | 2021-10-18 | 38 |  | completed |  | 23 | 2021-10-22
2 | Main building - Deck sheets fixing | 2021-09-15 | 2021-10-25 | 41 | Critical | Ongoing | Delayed due to steel structure erection | 23 | 2021-10-22
3 | Main building - Deck slab concrete - 4th floor | 2021-09-29 | 2021-10-21 | 23 |  | completed |  | 23 | 2021-10-22
3 | Main building - Deck slab concrete - 5th floor | 2021-09-27 | 2021-11-11 | 46 | Critical | Not Started |  | 23 | 2021-10-22
4 | Main building - Deck slab concrete - Terrace floor | 2021-09-20 | 2021-11-08 | 50 | Critical | Not Started | Delayed due to staircases erection | 23 | 2021-10-22
5 | Main building - Fire proof painting - 3rd floor | 2021-08-25 | 2021-10-30 | 67 | Critical | Ongoing | Grid 1 to 8 is in progress | 23 | 2021-10-22
6 | Main building - Blockwork at Ground floor | 2021-09-01 | 2021-10-29 | 59 | Critical | Ongoing | 97% completed. Balance works at staircase area | 23 | 2021-10-22
7 | Main building - Blockwork at 1st floor | 2021-08-26 | 2021-11-03 | 70 | Critical | Ongoing | Delayed due to deck slab concreting | 23 | 2021-10-22
8 | Main building - Blockwork at 2nd floor | 2021-08-16 | 2021-11-20 | 97 | Critical | Ongoing | Delayed due to deck slab concreting | 23 | 2021-10-22
9 | Main building - Blockwork at 3rd floor | 2021-10-03 | 2021-11-26 | 55 | Critical | Ongoing | Delayed due to deck slab concreting | 23 | 2021-10-22
10 | Main building - MEP 1st fix - ceiling at GF | 2021-10-05 | 2021-11-15 | 42 | Critical | Ongoing | Cable trays, Ducts, Pipes fixing in progress | 23 | 2021-10-22
11 | Main building - MEP 1st fix - ceiling at 1st floor | 2021-10-13 | 2021-11-30 | 49 | Critical | Ongoing | metal ceiling is completed & pipes fixing is in progress | 23 | 2021-10-22
12 | Main building - MEP 1st fix - ceiling at 2nd floor | 2021-11-27 | 2021-12-12 | 16 | Critical | Ongoing | metal ceiling & GSS pipe fixing is in progress | 23 | 2021-10-22
13 | Main building - Partition walls 1st fix at GF | 2021-09-01 | 2021-11-08 | 69 | Critical | Ongoing | 40% completed | 23 | 2021-10-22
14 | Main building - Partition walls 2nd fix at GF | 2021-09-08 | 2021-11-13 | 67 | Critical | Ongoing | 36% completed | 23 | 2021-10-22
15 | Main building - Partition walls final fix at GF | 2021-09-13 | 2021-11-18 | 67 | Critical | Ongoing | 14% completed | 23 | 2021-10-22
16 | Main building - Plastering at GF | 2021-09-22 | 2021-10-31 | 40 | Critical | Ongoing | 97% completed. | 23 | 2021-10-22
17 | Main building - Painting putty at GF | 2021-09-30 | 2021-11-24 | 56 | Critical | Ongoing |  | 23 | 2021-10-22
18 | Epoxy flooring at GF | 2022-04-03 | 2022-04-22 | 20 | Critical | Ongoing |  | 23 | 2021-10-22
19 | Main building - Plastering at 1st floor | 2021-09-08 | 2021-11-04 | 58 | Critical | Not Started | Delayed due to blockworks | 23 | 2021-10-22
20 | Main building - Partition walls 1st fix at 1st floor | 2021-09-20 | 2021-11-15 | 57 | Critical | Ongoing | 11% completed | 23 | 2021-10-22
21 | Main building - Partition walls 2nd fix at 1st floor | 2021-09-30 | 2021-11-20 | 52 | Critical | Not Started |  | 23 | 2021-10-22
22 | Main building - Partition walls final fix at 1st floor | 2021-10-05 | 2021-11-25 | 52 | Critical | Not Started |  | 23 | 2021-10-22
23 | DG Building - steel erection | 2021-09-09 | 2021-11-04 | 57 | Noncritical | Ongoing | Beam erections is in progress | 23 | 2021-10-22
24 | DG Building - Deck sheet fixing | 2021-09-11 | 2021-11-06 | 57 | Noncritical | Not Started |  | 23 | 2021-10-22
25 | Substation building - Blockworks | 2021-09-22 | 2021-10-28 | 37 | Critical | Ongoing |  | 23 | 2021-10-22
26 | Transformer - Trench & pedestal works | 2021-09-20 | 2021-11-05 | 47 | Critical | Ongoing | Trench raft,walls & equipment pedestals is in progress | 23 | 2021-10-22
27 | Road works - Phase 1 | 2021-12-17 | 2022-02-28 | 74 | Noncritical | Ongoing | south & west side is in progress | 23 | 2021-10-22
28 | Road works - Phase 2 | 2021-11-30 | 2022-03-15 | 106 | Noncritical | Ongoing | south & East side is in progress | 23 | 2021-10-22

## Status
Status
Ongoing
Not started
Suspended

## Type of Delay
Type of Delay
Critical
Non-Critical