## Executive Summary
S.No | Executive Summary | Date | Report No
1 | Site visit conducted by Gleeds on 24th September 2021 | 2021-09-24 | 19
2 | Revised phase 1 integrated baseline schedule – Rev 02 has been issued officially to all the stakeholders by gleeds on 20th September 2021 | 2021-09-24 | 19
3 | Gleeds has updated their revised Rev 02 integrated baseline schedule for phase 1 works till 24th September 2021. All the design & procurement updates on weekly basis is being sent to gleeds by AA | 2021-09-24 | 19
4 | Phase 1 completion is behind the schedule by 45 calendar days against the target completion date of 23rd May 2022 | 2021-09-24 | 19
5 | Main building - Erection of steel structure is ongoing very slowly, due to shortfall of resources – Structural steel – Received – 92%, Erected – 86% and Deck sheets – Received – 87%, Erected – 77%. Fireproof painting is in progress at 2nd floor level | 2021-09-24 | 19
6 | Main building – Blockworks – GF,1st & 2nd floor levels is in progress. MEP 1st fix – supports fixing in ceiling is in progress at ground & 1st floor levels. Partition walls 1st fix is in progress at ground & 1st floor levels. Plastering is in progress at ground floor level | 2021-09-24 | 19
7 | HSD building – Baffle wall & Backfilling is in progress | 2021-09-24 | 19
8 | Substation building – Form & rebar fixing for beams & slabs is completed for lower terrace level. Staging is in progress for upper terrace level | 2021-09-24 | 19
9 | Transformer foundation – MEP service manholes is in progress | 2021-09-24 | 19
10 | DG building – Superstructure works yet to be commenced | 2021-09-24 | 19
11 | WTP – Excavation is in progress | 2021-09-24 | 19
12 | External services & Development works – South & West sides for phase 1 & East side for phase 2 is in progress | 2021-09-24 | 19
13 | Quantum of delay as witnessed by Gleeds has been elaborated in this report through comparison against their revised timeline update along with current status of important base build deliverables | 2021-09-24 | 19
1 | Site visit conducted by Gleeds on 22nd October 2021 |  | 23
2 | Gleeds has updated their revised Rev 02 integrated baseline schedule for phase 1 works till 22nd October 2021. All the design & procurement activities have been updated on weekly basis, which is being sent to gleeds by AA | 2021-10-22 | 23
3 | Phase 1 completion is behind the schedule by 45 calendar days against the target completion date of 23rd May 2022 | 2021-10-22 | 23
4 | Main building – Structural steel – Received – 100%, Erected – 97% and Deck sheets – Received – 100%, Erected – 96%. Fireproof painting is in progress at 3rd floor level. Deck slab have been concreted for 4th floor level | 2021-10-22 | 23
5 | Main building – Blockworks – For GF,1st, 2nd & 3rd floor levels is in progress. MEP 1st fix – Pipes, Ducts & cable trays fixing is in progress at GF level, metal ceiling & pipes fixing is in progress at 1st floor level & metal ceiling is in progress at 2nd floor level. Partition walls 1st , 2nd & final fixes is in progress at ground floor level & 1st fix is in progress at 1st floor level. Plastering, Epoxy painting & Painting putty – For GF level is in progress. | 2021-10-22 | 23
6 | Substation building – Blockwork is in progress at GF | 2021-10-22 | 23
7 | Transformer foundation – Cable trench raft, walls & transformer pedestals works is in progress | 2021-10-22 | 23
8 | DG building – superstructure works - Beam erections is in progress | 2021-10-22 | 23
9 | External services & Development works – South & West sides for phase 1 & East side for phase 2 is in progress | 2021-10-22 | 23
10 | Quantum of delay as witnessed by Gleeds has been elaborated in this report through comparison against their revised timeline update along with current status of important base build deliverables | 2021-10-22 | 23