## Key Challanges (hidden)
S.No | Key Challenges | Date | Report No
1 | As per the current observations and the progress of works, in main building between grid 1 to 4 at 1st floor level, it is being delayed to commence the blockwork |  | 1
2 | In main building between grid 1 to 8, blockwork in ground floor must be accelerated, to commence MEP 1st fix and other finishing works |  | 1
3 | In main building between grid 1 to 4, it has been anticipated to complete the deck slab concrete at 2nd floor level – 12 Aug’21, 3rd floor level – 19 Aug’21 |  | 1
4 | In main building, for superstructure works, steel erections & deck sheet fixing progress have been delayed about one month between the grids 2 to 4 above 4th floor level due to non availability of materials

## Concerns
S.No | Concerns | Date | Report No
1 | 2 weeks lookahead Programme | 2021-09-24 | 19
2 | Vendors finalisation for MEP & finishing works by XX | 2021-09-24 | 19
3 | Material Submittals & Approvals | 2021-09-24 | 19
4 | Delay in completion of Shop drawings - GC works MEP works | 2021-09-24 | 19
5 | DG Building - Superstructure Works | 2021-09-24 | 19
6 | Transformer - Trench Works | 2021-09-24 | 19
1 | Delay in completion of Shop drawings - GC's MEP works | 2021-10-22 | 23
2 | DG Building - Superstructure Works | 2021-10-22 | 23
3 | Transformer - cable trench Works | 2021-10-22 | 23
4 | Substation Building - Block works, MEP and finishing works | 2021-10-22 | 23
5 | Delay in external MEP services on south & west sides for phase 1 | 2021-10-22 | 23

## Safety Concern
S.No | Safety Concerns | Date | Report No
1 | Gas cylinder kept in a non-designated area | 2021-12-03 | 28
2 | Absence of exclusion zone and traffic marshall in the external service road/area |  | 28
3 | Lack of competency supervision on work at height activities | 2021-12-10 | 29
4 | Cable routing is not maintained as per applicable standard | 2021-12-10 | 29
5 | Finishing materials are stored inappropriately ,and safe access is not provided. | 2021-10-12 | 29

## Quality Concern
S.No | Quality Concerns | Location | Date | Report No
1 | Space b/w the structure and partition supports is very less, not enough to fix the board and working space | Main Building | 2021-12-03 | 28
2 | Continuosly Observed Improper concrete finish in the GIS building Column | Substation Building | 2021-12-03 | 28
3 | Wall finishing activity is in progress before finishing of Masonry activities | Substation Building | 2021-12-03 | 28
4 | Cable trench MS angle frame not aligned and not supported | Substation Building | 2021-12-03 | 28
5 | Copper pipes laid haphazardly | Main Building | 2021-12-03 | 28
1 | Measurement box is not available, and mortar have been produced without measuring the quantity of cement and sand | Substation Building | 2021-12-10 | 29
2 | Shotcreting were damaged and sliding of soil over the reinforcements | WTP | 2021-12-10 | 29
3 | Cutouts should be completed before painting the surface | Main Building -1st floor | 2021-12-10 | 29
4 | Duct is sagging at elbow- Main building | Main Building - 2nd floor | 2021-12-10 | 29
5 | Rust formation on the surface of MS pipes -Terrace | Main Building- Terrace | 2021-12-10 | 29
6 | Chillers were not covered / protected- Terrace | Main Building - Terrace | 2021-12-10 | 29