## Key Milestone & Act this week
S.No | Key milestones and activities accomplished during this week | Report No | Date
1 | Main Building – Grid 3 to 4 – Deck sheet fixing 100% completed​ | 19 | 2021-09-24
2 | Main Building – Grid 4 to 5 – Deck sheet fixing for 5th & 6th floor levels is completed​ | 19 | 2021-09-24
3 | Main Building – Flashings, edge trimming & stud welding – Grid 1 to 4, terrace level have been completed. For grid 4 to 5, 5th & 6th floor levels have been completed​ | 19 | 2021-09-24
4 | Main Building – Fireproof painting have been commenced at 2nd floor level from grid 1 to 8​ | 19 | 2021-09-24
5 | Main Building – Grid 1 to 4 - Plastering works have been commenced at ground floor. MEP 1st fix in ceiling at 1st floor have been commenced. MEP 2nd fix, Pipes laying at ceiling level in ground floor have been commenced​ | 19 | 2021-09-24
6 | Substation Building – Form / Rebar fixing for beams & slabs at lower terrace level have been completed & ready to pour concrete​ | 19 | 2021-09-24
7 | East side road works – Phase 2 Area – GSB – 100% completed​ | 19 | 2021-09-24
8 | Temporary road works – In north side, it has been commenced | 19 | 2021-09-24
1 | Main Building – Grid 7 to 8 – Steel erection have been completed till terrace level & commenced for mumty levels | 23 | 2021-10-22
2 | Main Building – Grid 7 to 8 – Deck sheet fixing for 6th floor has been completed | 23 | 2021-10-22
3 | Main Building – Grid 7 to 8 – Flashings, Edge trimming & stud welding have been completed for 6th floor level & commenced for terrace floor level | 23 | 2021-10-22
4 | Main Building – 1st floor – Cable trays & FPS pipes fixing have been commenced | 23 | 2021-10-22
5 | Main Building – GSS pipeline fixing has been commenced at 2nd floor level | 23 | 2021-10-22
6 | Main Building – metal ceiling fixing for 1st floor level have been completed & at 2nd floor level has been commenced | 23 | 2021-10-22
7 | DG Building – Superstructure works, beams erection have been commenced | 23 | 2021-10-22
1 | Main Building – Grid 7 to 8 – Deck sheet fixing for terrace floor has been completed & commenced for mumty levels | 24 | 2021-10-29
2 | Main Building – 5th floor – Rebar fixing for deck slab between grid 1 to 4 has been commenced | 24 | 2021-10-29
3 | Main Building – Terrace floor – Chiller platforms between grid 3 to 7 have been completed | 24 | 2021-10-29
4 | Transformer – Fire wall rebar fixing has been commenced | 24 | 2021-10-29

## Status (hidden)
Status
completed
In progress
Not started

## Planned vs Actual-Elemental
S.NO | Elemental | Planned % | Actual % | Date | Report No
1 | Main Building | 58% | 42% | 2021-09-24 | 19
2 | DG Building | 43% | 28% | 2021-09-24 | 19
3 | Substation Building | 49% | 25% | 2021-09-24 | 19
4 | HSD Yard | 41% | 21% | 2021-09-24 | 19
5 | Fire pump room, WTP & STP | 36% | 7% | 2021-09-24 | 19
6 | Road works | 0% | 0% | 2021-09-24 | 19
7 | Hardscaping & Softscaping works | 0% | 0% | 2021-09-24 | 19
8 | Hardscaping & Softscaping works | 32% | 0% | 2021-10-22 | 23
7 | Fire pump room, WTP & STP | 41% | 24% | 2021-10-22 | 23
6 | Road works | 71% | 28% | 2021-10-22 | 23
5 | HSD Yard | 75% | 46% | 2021-10-22 | 23
3 | DG Building | 54% | 46% | 2021-10-22 | 23
4 | Substation Building | 62% | 37% | 2021-10-22 | 23
2 | Main Building | 75% | 57% | 2021-10-22 | 23
1 | Overall construction | 56% | 41% | 2021-10-22 | 23

## Report No
Report No | From Date | To Date
19 | 2021-09-17 | 2021-09-23
23 | 2021-10-16 | 2021-10-21
24 | 2021-10-22 | 2021-10-28
25 | 2021-10-29 | 2021-11-08
26 | 2021-11-09 | 2021-11-18
27 | 2021-11-19 | 2021-11-25
28 | 2021-11-26 | 2021-12-02
29 | 2021-12-03 | 2021-12-09
30 | 2021-12-10 | 2021-12-16

## Milestone Schedule
S.N | Phase | Elemental | Activity Description | Baseline Start | Baseline Finish | Actual / Forecast Start | Actual / Forecast Finish | Status | Date | Report No
1 | Design, material submittals & Procurement | Project | Project Start | 2020-06-01 | - | 2020-06-01 |  | completed | 2021-09-24 | 19
2 | Design, material submittals & Procurement | Project | Detailed Design (DD) | 2021-10-29 | 2021-02-15 | 2020-12-01 | 2021-03-12 | completed | 2021-09-24 | 19
3 | Design, material submittals & Procurement | Project | Construction Documents (GFC) | 2021-02-16 | 2021-03-07 | 2021-05-28 | 2021-06-14 | completed | 2021-09-24 | 19
4 | Design, material submittals & Procurement | Project | Shop Drawings | 2021-02-23 | 2021-07-26 | 2021-02-24 | 2021-11-22 | In progress | 2021-09-24 | 19
5 | Design, material submittals & Procurement | Project | Material submittals & Approvals | 2021-06-12 | 2021-08-24 | 2021-05-19 | 2021-11-22 | In progress | 2021-09-24 | 19
6 | Design, material submittals & Procurement | Project | Procurement of vendors by L&W | 2021-06-04 | 2021-07-26 | 2021-05-17 | 2021-10-23 | In progress | 2021-09-24 | 19
7 | Design, material submittals & Procurement | Project | Procurement of consultants | 2020-06-01 | 2021-03-15 | 2020-06-01 | 2021-05-20 | completed | 2021-09-24 | 19
8 | Design, material submittals & Procurement | Project | Procurement of subcontract packages | 2020-09-15 | 2021-04-29 | 2020-09-09 | 2021-05-17 | completed | 2021-09-24 | 19
9 | Design, material submittals & Procurement | Project | Procurement of FIM | 2021-07-03 | 2021-11-05 | 2021-07-03 | 2021-11-15 | In progress | 2021-09-24 | 19
10 | Design, material submittals & Procurement | Project | Procurement of GC's MEP items | 2021-06-11 | 2021-12-08 | 2021-06-10 | 2022-04-12 | In progress | 2021-09-24 | 19
1 | Construction | Project | Construction Start | 2020-11-12 | - | 2020-11-20 | - | completed | 2021-09-24 | 19
2 | Construction | Main Building | Piling works | 2021-01-25 | 2021-04-02 | 2021-01-25 | 2021-04-22 | completed | 2021-09-24 | 19
3 | Construction | Main Building | Substructure | 2021-02-17 | 2021-04-21 | 2021-03-09 | 2021-07-19 | completed | 2021-09-24 | 19
4 | Construction | Main Building | Superstructure | 2021-05-22 | 2021-09-15 | 2021-05-22 | 2021-10-15 | In progress | 2021-09-24 | 19
5 | Construction | Main Building | Deck slab concreting | 2021-07-16 | 2021-10-01 | 2021-07-16 | 2021-12-08 | In progress | 2021-09-24 | 19
6 | Construction | Main Building | MEP / Finishing works | 2021-07-30 | 2022-04-30 | 2021-07-28 | 2022-06-30 | In progress | 2021-09-24 | 19
7 | Construction | Main Building | Power on |  | 2022-03-01 | - | 2022-04-20 | Not started | 2021-09-24 | 19
8 | Construction | Main Building | Testing & commissioning | 2022-02-22 | 2022-05-23 | 2022-04-04 | 2022-07-23 | Not started | 2021-09-24 | 19
9 | Construction | Main Building | Project hand over |  | 2022-05-23 |  | 2022-07-23 | Not started | 2021-09-24 | 19
10 | Construction | Utility buildings / External development | DG Building | 2021-04-23 | 2022-02-19 | 2021-04-23 | 2022-04-07 | In progress | 2021-09-24 | 19
11 | Construction | Utility buildings / External development | HSD | 2021-05-31 | 2012-12-24 | 2021-05-31 | 2022-02-25 | In progress | 2021-09-24 | 19
12 | Construction | Utility buildings / External development | Substation Building | 2021-06-02 | 2022-03-02 | 2021-06-02 | 2022-03-26 | In progress | 2021-09-24 | 19
13 | Construction | Utility buildings / External development | Fire pump room, WTP & STP | 2021-07-27 | 2022-03-01 | 2021-08-23 | 2022-04-20 | In progress | 2021-09-24 | 19
14 | Construction | Utility buildings / External development | Road Works | 2021-07-05 | 2021-12-17 | 2021-08-09 | 2022-02-01 | In progress | 2021-09-24 | 19
15 | Construction | Utility buildings / External development | Landscaping Works | 2021-09-04 | 2022-02-19 | 2021-12-30 | 2022-03-30 | Not started | 2021-09-24 | 19

## 2 Weeks Lookhead Schedule
S.N | Phase | Elemental | WBS-1 | WBS-2 | Activity Name | Planned Start | Planned Finish | % Completion | Responsible for Action | Status | Date | Report No
1 | Shop Drawings | Project |  |  | MEP shop Drawings / Approvals - GC's Scope | 2021-06-04 | 2021-11-22 |  | ACX / L&W | In Progress | 2021-09-24 | 19
2 | Material submittals & Approvals | Project |  |  | Material submittals / Approvals - GC's Scope | 2021-05-19 | 2021-11-23 |  | ACX / L&W | In Progress | 2021-09-24 | 19
3 | Procurement | Project |  |  | Main building - Delivery of steel structure & Deck sheets | 2021-05-07 | 2021-09-30 |  | ACX / JSSL | In Progress | 2021-09-24 | 19
4 | Procurement | Project |  |  | Procurement of MEP / finishing materials under GC's scope | 2021-06-10 | 2022-02-12 |  | ACX / L&W | In Progress | 2021-09-24 | 19
5 | Procurement | Project |  |  | Procurement of FIM Materials | 2021-07-03 | 2021-11-15 |  | ACX | In Progress | 2021-09-24 | 19
6 | Construction | Main Building | Steel Structure Erection |  | Grid 4 to 5 | 2021-07-17 | 2021-09-28 |  | ACX / JSSL | In Progress | 2021-09-24 | 19
7 | Construction | Main Building | Steel Structure Erection |  | Grid 5 to 6 | 2021-07-22 | 2021-10-05 |  | ACX / JSSL | In Progress | 2021-09-24 | 19
8 | Construction | Main Building | Steel Structure Erection |  | Grid 6 to 7 | 2021-07-28 | 2021-10-06 |  | ACX / JSSL | In Progress | 2021-09-24 | 19
9 | Construction | Main Building | Steel Structure Erection |  | Grid 7 to 8 | 2021-08-09 | 2021-10-09 |  | ACX / JSSL | In Progress | 2021-09-24 | 19
10 | Construction | Main Building | Deck Sheets |  | Grid 4 to 5 | 2021-09-01 | 2021-10-02 |  | ACX / JSSL | In Progress | 2021-09-24 | 19
11 | Construction | Main Building | Deck Sheets |  | Grid 5 to 6 | 2021-09-04 | 2021-10-08 |  | ACX / JSSL | In Progress | 2021-09-24 | 19
12 | Construction | Main Building | Deck Sheets |  | Grid 6 to 7 | 2021-09-11 | 2021-10-12 |  | ACX / JSSL | In Progress | 2021-09-24 | 19
13 | Construction | Main Building | Deck Sheets |  | Grid 7 to 8 | 2021-08-13 | 2021-10-15 |  | ACX / JSSL | In Progress | 2021-09-24 | 19
14 | Construction | Main Building | Deck slab concrete | Terrace floor | Grid 1 to 4 | 2021-10-01 | 2021-10-07 |  | ACX / L&W | In Progress | 2021-09-24 | 19
15 | Construction | Main Building | Deck slab concrete | Terrace floor | Grid 4 to 8 | 2021-10-08 | 2021-10-14 |  | ACX / L&W | In Progress | 2021-09-24 | 19
16 | Construction | Main Building | Internal MEP & Finishing works | Ground floor | Blockwork | 2021-07-28 | 2021-09-30 |  | ACX / L&W | In Progress | 2021-09-24 | 19
17 | Construction | Main Building | Internal MEP & Finishing works | Ground floor | MEP 1st fix - Ceiling | 2021-09-01 | 2021-10-30 |  | ACX / L&W | In Progress | 2021-09-24 | 19
18 | Construction | Main Building | Internal MEP & Finishing works | Ground floor | Partition works - 1st fix | 2021-09-01 | 2021-10-10 |  | ACX / L&W | In Progress | 2021-09-24 | 19
19 | Construction | Main Building | Internal MEP & Finishing works | Ground floor | Plastering | 2021-09-15 | 2021-10-06 |  | ACX / L&W | In Progress | 2021-09-24 | 19
20 | Construction | Main Building | Internal MEP & Finishing works | 1st floor | Blockwork | 2021-08-17 | 2021-10-08 |  | ACX / L&W | Not started | 2021-09-24 | 19
21 | Construction | Main Building | Internal MEP & Finishing works | 1st floor | MEP 1st fix - Ceiling | 2021-09-15 | 2021-11-05 |  | ACX / L&W | Not started | 2021-09-24 | 19
22 | Construction | Main Building | Internal MEP & Finishing works | 1st floor | Partition works - 1st fix | 2021-09-21 | 2021-10-17 |  | ACX / L&W | Not started | 2021-09-24 | 19
23 | Construction | Main Building | Internal MEP & Finishing works | 2nd floor | Blockwork | 2021-09-01 | 2021-10-15 |  | ACX / L&W | In Progress | 2021-09-24 | 19
24 | Construction | Main Building | Internal MEP & Finishing works | 2nd floor | Fire Proof Painting - Columns / Beams | 2021-09-04 | 2021-09-30 |  | ACX / L&W | Not started | 2021-09-24 | 19
25 | Construction | Main Building | Internal MEP & Finishing works | 2nd floor | MEP 1st fix - Ceiling | 2021-10-06 | 2021-11-17 |  | ACX / L&W | Not started | 2021-09-24 | 19
1 | Shop Drawings | Project |  |  | MEP shop Drawings / Approvals - GC's Scope | 2021-06-04 | 2021-11-02 |  | ACX / L&W | In Progress | 2021-10-22 | 23
2 | Material submittals & Approvals | Project |  |  | Material submittals / Approvals - GC's Scope | 2021-05-19 | 2021-12-13 |  | ACX / L&W | In Progress | 2021-10-22 | 23
3 | Procurement | Project |  |  | Procurement of MEP / finishing materials under GC's scope | 2021-06-10 | 2022-02-02 |  | ACX / L&W | In Progress | 2021-10-22 | 23
4 | Procurement | Project |  |  | Procurement of FIM Materials | 2021-07-03 | 2021-11-19 |  | ACX | In Progress | 2021-10-22 | 23
5 | Construction | Main Building | Deck Sheets |  | Grid 7 to 8 | 2021-08-13 | 2021-10-25 |  | ACX / JSSL | In Progress | 2021-10-22 | 23
6 | Construction | Main Building | Deck slab concrete | Terrace floor | Grid 1 to 4 | 2021-10-26 | 2021-11-01 |  | ACX / L&W | Not started | 2021-10-22 | 23
7 | Construction | Main Building | Deck slab concrete | Terrace floor | Grid 4 to 8 | 2021-11-02 | 2021-11-08 |  | ACX / L&W | Not started | 2021-10-22 | 23
8 | Construction | Main Building | Deck slab concrete | 5th floor | Grid 1 to 4 | 2021-10-27 | 2021-11-04 |  | ACX / L&W | Not started | 2021-10-22 | 23
9 | Construction | Main Building | Deck slab concrete | 5th floor | Grid 4 to 8 | 2021-11-03 | 2021-11-11 |  | ACX / L&W | Not started | 2021-10-22 | 23
10 | Construction | Main Building | Internal MEP & Finishing works | Ground floor | Blockwork | 2021-07-28 | 2021-10-29 |  | ACX / L&W | In Progress | 2021-10-22 | 23
11 | Construction | Main Building | Internal MEP & Finishing works | Ground floor | MEP 1st fix - Ceiling | 2021-08-12 | 2021-11-15 |  | ACX / L&W | In Progress | 2021-10-22 | 23
12 | Construction | Main Building | Internal MEP & Finishing works | Ground floor | Partition works - 1st fix | 2021-09-01 | 2021-11-08 |  | ACX / L&W | In Progress | 2021-10-22 | 23
13 | Construction | Main Building | Internal MEP & Finishing works | Ground floor | Partition works - 2nd fix | 2021-09-15 | 2021-11-13 |  | ACX / L&W | In Progress | 2021-10-22 | 23
14 | Construction | Main Building | Internal MEP & Finishing works | Ground floor | Partition works - final fix | 2021-10-01 | 2021-11-18 |  | ACX / L&W | In Progress | 2021-10-22 | 23
15 | Construction | Main Building | Internal MEP & Finishing works | Ground floor | Plastering | 2021-09-15 | 2021-10-31 |  | ACX / L&W | In Progress | 2021-10-22 | 23
16 | Construction | Main Building | Internal MEP & Finishing works | Ground floor | Painting putty | 2021-09-21 | 2021-11-24 |  | ACX / L&W | In Progress | 2021-10-22 | 23
17 | Construction | Main Building | Internal MEP & Finishing works | Ground floor | Epoxy flooring | 2021-09-01 | 2022-04-22 |  | ACX / L&W | In Progress | 2021-10-22 | 23
18 | Construction | Main Building | Internal MEP & Finishing works | 1st floor | Blockwork | 2021-08-17 | 2021-11-03 |  | ACX / L&W | In Progress | 2021-10-22 | 23
19 | Construction | Main Building | Internal MEP & Finishing works | 1st floor | MEP 1st fix - Ceiling | 2021-08-17 | 2021-11-30 |  | ACX / L&W | In Progress | 2021-10-22 | 23
20 | Construction | Main Building | Internal MEP & Finishing works | 1st floor | Partition works - 1st fix | 2021-09-21 | 2021-11-15 |  | ACX / L&W | In Progress | 2021-10-22 | 23
21 | Construction | Main Building | Internal MEP & Finishing works | 1st floor | Partition works - 2nd fix | 2021-10-25 | 2021-11-20 |  | ACX / L&W | Not started | 2021-10-22 | 23
22 | Construction | Main Building | Internal MEP & Finishing works | 1st floor | Partition works - Final fix | 2021-11-01 | 2021-11-25 |  | ACX / L&W | Not started | 2021-10-22 | 23
23 | Construction | Main Building | Internal MEP & Finishing works | 1st floor | Plastering | 2021-10-23 | 2021-11-10 |  | ACX / L&W | Not started | 2021-10-22 | 23
24 | Construction | Main Building | Internal MEP & Finishing works | 2nd floor | Blockwork | 2021-09-01 | 2021-11-20 |  | ACX / L&W | In Progress | 2021-10-22 | 23
25 | Construction | Main Building | Internal MEP & Finishing works | 2nd floor | MEP 1st fix - Ceiling | 2021-10-11 | 2021-12-12 |  | ACX / L&W | In Progress | 2021-10-22 | 23
26 | Construction | Main Building | Internal MEP & Finishing works | 2nd floor | Partition works - 1st fix | 2021-10-23 | 2021-12-09 |  | ACX / L&W | Not started | 2021-10-22 | 23
27 | Construction | Main Building | Internal MEP & Finishing works | 3rd floor | Blockwork | 2021-10-11 | 2021-11-26 |  | ACX / L&W | In progress | 2021-10-22 | 23
28 | Construction | Main Building | Internal MEP & Finishing works | 3rd floor | Fire Proof Painting - Columns / Beams | 2021-10-11 | 2021-10-30 |  | ACX / L&W | In progress | 2021-10-22 | 23
29 | Construction | DG Building | Superstructure works | Roof | Steel erection | 2021-10-12 | 2021-11-04 |  | ACX / JSSL | In progress | 2021-10-22 | 23
30 | Construction | DG Building | Superstructure works | Roof | Deck sheet fixing | 2021-10-23 | 2021-11-06 |  | ACX / JSSL | Not started | 2021-10-22 | 23
31 | Construction | Substation Building | Superstructure works | Ground floor | Blockwork | 2021-10-06 | 2021-11-01 |  | ACX / L&W | In progress | 2021-10-22 | 23
32 | Construction | Transformer yard | Foundations |  | Cable trenches raft | 2021-09-28 | 2021-10-31 |  | ACX / L&W | In progress | 2021-10-22 | 23
33 | Construction | Transformer yard | Foundations |  | Cable trench walls | 2021-10-10 | 2021-11-05 |  | ACX / L&W | In progress | 2021-10-22 | 23
34 | Construction | Transformer yard | Foundations |  | Equipment pedestals | 2021-10-14 | 2021-10-25 |  | ACX / L&W | In progress | 2021-10-22 | 23
35 | Construction | Road works |  |  | Phase 1 | 2021-08-23 | 2022-02-28 |  | ACX / L&W | In progress | 2021-10-22 | 23
36 | Construction | Road works |  |  | Phase 2 | 2021-08-09 | 2022-03-15 |  | ACX / L&W | In progress | 2021-10-22 | 23

## L-2 Programme
S.N | Phase | Elemental | WBS-1 | WBS-2 | Activity Name | Planned Start | Planned Finish | % Completion | Responsible for Action | Status | Date | Report No
1 | Design & Engineering | Project |  |  | Master Plan | 2020-06-01 | 2020-06-30 |  | AA | completed | 2021-10-22 | 23
2 | Design & Engineering | Project |  |  | Concept Design & Review | 2020-07-31 | 2020-11-11 |  | AA | completed | 2021-10-22 | 23
3 | Design & Engineering | Project |  |  | Detailed Design | 2020-12-01 | 2021-06-08 |  | AA | completed | 2021-10-22 | 23
4 | Design & Engineering | Project |  |  | Detailed Design Peer Review | 2021-01-04 | 2021-06-15 |  | AA | completed | 2021-10-22 | 23
5 | Design & Engineering | Project |  |  | Construction Documents | 2021-01-10 | 2021-06-14 |  | AA | completed | 2021-10-22 | 23
6 | Design & Engineering | Project |  |  | Steel Structure Design | 2021-03-25 | 2021-05-10 |  | AA | completed | 2021-10-22 | 23
7 | Design & Engineering | Project |  |  | Shop Drawings | 2021-03-15 | 2021-10-30 |  | All | In Progress | 2021-10-22 | 23
8 | Authority Submissions and Approvals | Project |  |  | Authority Submissions and Approvals | 2020-07-06 | 2022-05-23 |  | All | In Progress | 2021-10-22 | 23
9 | Material submittals & Approvals | Project |  |  | Material submittals & Approvals | 2021-06-12 | 2021-11-22 |  | All | In Progress | 2021-10-22 | 23
10 | Procurement | Project | Consultants |  | Consultants | 2020-06-01 | 2021-05-20 |  | AA | completed | 2021-10-22 | 23
11 | Procurement | Project | Sub Contract Work Packages |  | Earthwork Package | 2020-09-09 | 2020-11-11 |  | AA | completed | 2021-10-22 | 23
12 | Procurement | Project | Sub Contract Work Packages |  | Piling Package | 2020-10-19 | 2020-12-16 |  | AA | completed | 2021-10-22 | 23
13 | Procurement | Project | Sub Contract Work Packages |  | Steel Structure Package | 2020-12-10 | 2021-02-22 |  | AA | completed | 2021-10-22 | 23
14 | Procurement | Project | Sub Contract Work Packages |  | Substation Package | 2021-01-17 | 2021-04-19 |  | AA | completed | 2021-10-22 | 23
15 | Procurement | Project | Sub Contract Work Packages |  | General Contractor Package | 2020-12-29 | 2021-05-17 |  | AA | completed | 2021-10-22 | 23
16 | Procurement | Project | Procurement - Long Lead items |  | FIM (Free issue Materials) | 2021-07-03 | 2021-11-15 |  | AA | In Progress | 2021-10-22 | 23
17 | Procurement | Project | Procurement - Long Lead items |  | GIS | 2021-05-29 | 2021-12-28 |  | All | In Progress | 2021-10-22 | 23
18 | Procurement | Project | Procurement - Long Lead items |  | Transformers | 2021-07-21 | 2022-01-03 |  | All | In Progress | 2021-10-22 | 23
19 | Procurement | Project | Procurement - Long Lead items |  | Steel Structure | 2021-05-01 | 2021-10-15 |  | All | completed | 2021-10-22 | 23
20 | Procurement | Project | Procurement - Long Lead items |  | GC Works Materials | 2021-06-10 | 2022-02-12 |  | XX | In progress | 2021-10-22 | 23
21 | General | Project |  |  | GC Mobilisation | 2021-05-18 | 2021-06-01 |  | AA | completed | 2021-10-22 | 23
22 | Construction | Main Building |  |  | Piling Works | 2021-01-23 | 2021-03-23 |  | XX | completed | 2021-10-22 | 23
23 | Construction | Main Building |  |  | Substructure Works | 2020-12-23 | 2021-07-19 |  | XX | completed | 2021-10-22 | 23
24 | Construction | Main Building |  |  | Superstructure works | 2021-05-21 | 2021-10-25 |  | XX | In progress | 2021-10-22 | 23
25 | Construction | Main Building |  |  | Deck slab concreting | 2021-07-16 | 2021-11-19 |  | XX | In progress | 2021-10-22 | 23
26 | Construction | Main Building |  |  | MEP and Internal Finishes | 2021-07-29 | 2022-04-30 |  | XX | In progress | 2021-10-22 | 23
27 | Construction | Main Building |  |  | External Façade | 2021-12-10 | 2022-04-19 |  | XX | Not started | 2021-10-22 | 23
28 | Construction | Main Building |  |  | Elevators | 2021-11-26 | 2022-04-30 |  | XX | Not started | 2021-10-22 | 23
29 | Construction | DG Building |  |  | DG Building | 2021-04-23 | 2022-04-07 |  | XX | In progress | 2021-10-22 | 23
30 | Construction | Substation Building |  |  | Substation Building | 2021-06-02 | 2022-03-26 |  | XX | In progress | 2021-10-22 | 23
31 | Construction | HSD |  |  | HSD | 2021-05-31 | 2022-02-25 |  | XX | In progress | 2021-10-22 | 23
32 | Construction | WTP, STP & Fire pump room |  |  | WTP, STP & Fire pump room | 2021-07-27 | 2022-04-26 |  | XX | In progress | 2021-10-22 | 23
33 | Construction | External Development works |  |  | External Development works | 2021-08-09 | 2022-03-30 |  | XX | In progress | 2021-10-22 | 23
34 | Power Up | Project |  |  | Power Up |  | 2022-03-01 |  | XX | Not started | 2021-10-22 | 23
35 | Testing and Commissioning | Project |  |  | Testing and Commissioning | 2022-02-22 | 2022-05-23 |  | XX | Not started | 2021-10-22 | 23
36 | Project Handover | Project |  |  | Project Handover |  | 2022-05-23 |  | XX | Not started | 2021-10-22 | 23
1 | Design & Engineering | Design & Engineering |  |  | Master Plan | 2020-06-01 | 2020-06-30 |  | AA | completed | 2021-10-29 | 24
2 | Design & Engineering | Design & Engineering |  |  | Concept Design & Review | 2020-07-31 | 2020-11-11 |  | AA | completed | 2021-10-29 | 24
3 | Design & Engineering | Design & Engineering |  |  | Detailed Design | 2020-12-01 | 2021-06-08 |  | AA | completed | 2021-10-29 | 24
4 | Design & Engineering | Design & Engineering |  |  | Detailed Design Peer Review | 2021-01-04 | 2021-06-15 |  | AA | completed | 2021-10-29 | 24
5 | Design & Engineering | Design & Engineering |  |  | Construction Documents | 2021-01-10 | 2021-06-14 |  | AA | completed | 2021-10-29 | 24
6 | Design & Engineering | Design & Engineering |  |  | Steel Structure Design | 2021-03-25 | 2021-05-10 |  | All | completed | 2021-10-29 | 24
7 | Design & Engineering | Design & Engineering |  |  | Shop Drawings | 2021-03-15 | 2021-11-02 |  | XX | In Progress | 2021-10-29 | 24
8 | Authority Submissions and Approvals | Authority Submissions and Approvals |  |  | Authority Submissions and Approvals | 2020-07-06 | 2022-05-23 |  | XX | In Progress | 2021-10-29 | 24
9 | Material submittals & Approvals | Material submittals & Approvals |  |  | Material submittals & Approvals | 2021-06-12 | 2021-11-22 |  | AA | In Progress | 2021-10-29 | 24
10 | Procurement | Procurement | Consultants |  | Consultants | 2020-06-01 | 2021-05-20 |  | AA | completed | 2021-10-29 | 24
11 | Procurement | Procurement | Sub Contract Work Packages |  | Earthwork Package | 2020-09-09 | 2020-11-11 |  | AA | completed | 2021-10-29 | 24
12 | Procurement | Procurement | Sub Contract Work Packages |  | Piling Package | 2020-10-19 | 2020-12-16 |  | AA | completed | 2021-10-29 | 24
13 | Procurement | Procurement | Sub Contract Work Packages |  | Steel Structure Package | 2020-12-10 | 2021-02-22 |  | XX | completed | 2021-10-29 | 24
14 | Procurement | Procurement | Sub Contract Work Packages |  | Substation Package | 2021-01-17 | 2021-04-19 |  | XX | completed | 2021-10-29 | 24
15 | Procurement | Procurement | Sub Contract Work Packages |  | General Contractor Package | 2020-12-29 | 2021-05-17 |  | AA | completed | 2021-10-29 | 24
16 | Procurement | Procurement | Procurement - Long Lead items |  | FIM (Free issue Materials) | 2021-07-03 | 2021-11-15 |  | AA | In Progress | 2021-10-29 | 24
17 | Procurement | Procurement | Procurement - Long Lead items |  | GIS | 2021-05-29 | 2021-12-28 |  | AA | In Progress | 2021-10-29 | 24
18 | Procurement | Procurement | Procurement - Long Lead items |  | Transformers | 2021-07-21 | 2022-01-03 |  | AA | In Progress | 2021-10-29 | 24
19 | Procurement | Procurement | Procurement - Long Lead items |  | Steel Structure | 2021-05-01 | 2021-10-15 |  | XX | completed | 2021-10-29 | 24
20 | Procurement | Procurement | Procurement - Long Lead items |  | GC Works Materials | 2021-06-10 | 2022-02-02 |  | XX | In progress | 2021-10-29 | 24
21 | General | General | General |  | GC Mobilisation | 2021-05-18 | 2021-06-01 |  | AA | completed | 2021-10-29 | 24
22 | Construction | Main Building | Main Building |  | Piling Works | 2021-01-23 | 2021-03-23 |  | AA | completed | 2021-10-29 | 24
23 | Construction | Main Building | Main Building |  | Substructure Works | 2020-12-23 | 2021-07-19 |  | AA | completed | 2021-10-29 | 24
24 | Construction | Main Building | Main Building |  | Superstructure works | 2021-05-21 | 2021-10-23 |  | AA | In progress | 2021-10-29 | 24
25 | Construction | Main Building | Main Building |  | Deck slab concreting | 2021-07-16 | 2021-11-25 |  | XX | In progress | 2021-10-29 | 24
26 | Construction | Main Building | Main Building |  | MEP and Internal Finishes | 2021-07-29 | 2022-04-30 |  | XX | In progress | 2021-10-29 | 24
27 | Construction | Main Building | Main Building |  | External Façade | 2021-11-26 | 2021-04-19 |  | AA | Not started | 2021-10-29 | 24
28 | Construction | Main Building | Main Building |  | Elevators | 2021-11-26 | 2022-04-30 |  | AA | Not started | 2021-10-29 | 24
29 | Construction | DG Building | DG Building |  | DG Building | 2021-04-23 | 2022-04-07 |  | AA | In progress | 2021-10-29 | 24
30 | Construction | Substation Building | Substation Building |  | Substation Building | 2021-06-02 | 2022-03-26 |  | AA | In progress | 2021-10-29 | 24
31 | Construction | HSD | HSD |  | HSD | 2021-05-31 | 2022-02-25 |  | XX | In progress | 2021-10-29 | 24
32 | Construction | WTP, STP & Fire pump room | WTP, STP & Fire pump room |  | WTP, STP & Fire pump room | 2021-07-27 | 2022-04-26 |  | XX | In progress | 2021-10-29 | 24
33 | Construction | External Development works | External Development works |  | External Development works | 2021-08-09 | 2022-03-30 |  | AA | In progress | 2021-10-29 | 24
34 | Power Up | Power Up | Power Up |  | Power Up |  | 2022-03-01 |  | AA | Not started | 2021-10-29 | 24
35 | Testing and Commissioning | Testing and Commissioning | Testing and Commissioning |  | Testing and Commissioning | 2022-02-22 | 2022-05-23 |  | AA | Not started | 2021-10-29 | 24
36 | Project Handover | Project |  |  | Project Handover |  | 2022-05-23 |  | AA | Not started | 2021-10-29 | 24

## Planned vs Actual-Project Level
Level | Planned% | Actual% | Date | Report No
Design & construction documents | 100% | 100% | 2021-09-24 | 19
Shop Drawings | 100% | 75% | 2021-09-24 | 19
Statutory Approvals | 100% | 100% | 2021-09-24 | 19
Material submittals & Approvals | 100% | 84% | 2021-09-24 | 19
Procurement | 87% | 65% | 2021-09-24 | 19
Construction | 52% | 43% | 2021-09-24 | 19
Testing & Commissioning | 0% | 0% | 2021-09-24 | 19
Project | 68% | 57% | 2021-09-24 | 19

## Project Status
Overall Project Baseline Start Date | Overall Project Baseline Finish Date | overall Project Actual Start Date | Overall Project Anticipated Finish Date | Overall Delay of Project | Date | Report No
2020-06-01 | 2022-05-23 | 2020-06-01 | 2022-07-23 | 62 | 2021-09-24 | 19
2020-06-01 | 2022-05-23 | 2020-06-01 | 2022-07-18 | 57 | 2021-10-22 | 23

## Planned Vs Actual- Activitywise
Elemental | Activity Name | Planned % | Actual % | Date | Report No
Main Building | Steel Structure erection | 100% | 86% | 2021-09-24 | 19
Main Building | Deck Sheet fixing | 100% | 77% | 2021-09-24 | 19
Main Building | Deck slab concrete | 95% | 50% | 2021-09-24 | 19
Main Building | Fire Proof Painting | 64% | 18% | 2021-09-24 | 19
Main Building | Blockwork - GF | 100% | 96% | 2021-09-24 | 19
Main Building | Blockwork - 1st floor | 100% | 32% | 2021-09-24 | 19
Main Building | Blockwork - 2nd floor | 100% | 14% | 2021-09-24 | 19
Main Building | MEP 1st fix ceiling - GF | 47% | 36% | 2021-09-24 | 19
Main Building | Partition walls 1st fix - GF | 100% | 7% | 2021-09-24 | 19
Main Building | Plastering - GF | 100% | 85% | 2021-09-24 | 19
Main Building | MEP 1st fix ceiling - 1st floor | 34% | 1% | 2021-09-24 | 19
Main Building | Partition walls 1st fix - 1st floor | 84% | 2% | 2021-09-24 | 19
DG Building | Steel erection | 100% | 0% | 2021-09-24 | 19
DG Building | Deck sheet fixing | 100% | 0% | 2021-09-24 | 19
Substation building | FW for beams / Slabs - Lower Terrace | 100% | 100% | 2021-09-24 | 19
Substation building | Rebar fixing for beams / Slabs - Lower Terrace | 100% | 100% | 2021-09-24 | 19
Substation building | Lower Terrace Concreting | 100% | 0% | 2021-09-24 | 19
HSD Building | Backfilling | 100% | 89% | 2021-09-24 | 19
Main Building | Steel Structure erection | 100% | 97% | 2021-10-22 | 23
Main Building | Deck Sheet fixing | 100% | 96% | 2021-10-22 | 23
Main Building | Deck slab concrete | 100% | 67% | 2021-10-22 | 23
Main Building | Fire Proof Painting | 84% | 29% | 2021-10-22 | 23
Main Building | Blockwork - GF | 100% | 97% | 2021-10-22 | 23
Main Building | Blockwork - 1st floor | 100% | 63% | 2021-10-22 | 23
Main Building | Blockwork - 2nd floor | 100% | 33% | 2021-10-22 | 23
Main Building | Blockwork - 3rd floor | 100% | 10% | 2021-10-22 | 23
Main Building | MEP 1st fix - GF | 100% | 58% | 2021-10-22 | 23
Main Building | Partition walls 1st fix - GF | 100% | 45% | 2021-10-22 | 23
Main Building | Partition walls 2nd fix ( 1 side board) - GF | 100% | 36% | 2021-10-22 | 23
Main Building | Partition walls final fix ( outer side board) - GF | 100% | 15% | 2021-10-22 | 23
Main Building | Plastering - GF | 100% | 97% | 2021-10-22 | 23
Main Building | Painting putty - GF | 100% | 1% | 2021-10-22 | 23
Main Building | Epoxy painting - GF | 0% | 22% | 2021-10-22 | 23
Main Building | MEP 1st fix - 1st floor | 100% | 36% | 2021-10-22 | 23
Main Building | Partition walls 1st fix - 1st floor | 100% | 11% | 2021-10-22 | 23
Main Building | Partition walls 2nd fix ( 1 side board) - 1st floor | 100% | 0% | 2021-10-22 | 23
Main Building | Plastering - 1st floor | 100% | 0% | 2021-10-22 | 23
Main Building | MEP 1st fix - 2nd floor | 83% | 22% | 2021-10-22 | 23
DG Building | Steel erection | 100% | 48% | 2021-10-22 | 23
DG Building | Deck sheet fixing | 100% | 0% | 2021-10-22 | 23
Substation building | Lower Terrace Concreting | 100% | 100% | 2021-10-22 | 23
Substation building | Columns to upper terrace | 100% | 100% | 2021-10-22 | 23
Substation building | FW for beams / Slabs - Upper Terrace | 100% | 100% | 2021-10-22 | 23
Substation building | Rebar fixing for beams / Slabs - Upper Terrace | 100% | 100% | 2021-10-22 | 23
Substation building | Upper Terrace Concreting | 100% | 100% | 2021-10-22 | 23
Substation building | Block work | 100% | 15% | 2021-10-22 | 23
HSD Building | Backfilling | 100% | 89% | 2021-10-22 | 23
Transformer | Cable trench Raft | 100% | 15% | 2021-10-22 | 23
Transformer | Cable trench walls | 100% | 19% | 2021-10-22 | 23
Transformer | Equipment pedestals | 100% | 67% | 2021-10-22 | 23