## Non Conformance Report
Contractor Name | Date | OPEN | CLOSED | RAISED | Report No
EE | 2021-09-24 | 0 | 1 | 1 | 19
TT | 2021-09-24 | 0 | 8 | 8 | 19
FF | 2021-09-24 | 1 | 8 | 9 | 19
AA | 2021-09-24 | 0 | 2 | 2 | 19
QQ | 2021-09-24 | 2 | 6 | 8 | 19
FF | 2021-09-24 | 2 | 3 | 5 | 19
EE | 2021-10-01 | 0 | 1 | 1 | 20
TT | 2021-10-01 | 0 | 8 | 8 | 20
FF | 2021-10-01 | 1 | 8 | 9 | 20
AA | 2021-10-01 | 0 | 2 | 2 | 20
QQ | 2021-10-01 | 0 | 8 | 8 | 20
FF | 2021-10-01 | 2 | 3 | 5 | 20
EE | 2021-10-08 | 0 | 1 | 1 | 21
TT | 2021-10-08 | 0 | 8 | 8 | 21
FF | 2021-10-08 | 1 | 8 | 9 | 21
AA | 2021-10-08 | 0 | 2 | 2 | 21
QQ | 2021-10-08 | 3 | 8 | 11 | 21
FF | 2021-10-08 | 2 | 3 | 5 | 21
EE | 2021-10-21 | 0 | 1 | 1 | 23
TT | 2021-10-21 | 0 | 8 | 8 | 23
FF | 2021-10-21 | 1 | 8 | 9 | 23
AA | 2021-10-21 | 0 | 2 | 2 | 23
QQ | 2021-10-21 | 9 | 13 | 22 | 23
FF | 2021-10-21 | 2 | 3 | 5 | 23
EE | 2021-10-28 | 0 | 1 | 1 | 24
TT | 2021-10-28 | 0 | 8 | 8 | 24
FF | 2021-10-28 | 1 | 8 | 9 | 24
AA | 2021-10-28 | 0 | 2 | 2 | 24
QQ | 2021-10-28 | 5 | 23 | 28 | 24
FF | 2021-10-28 | 2 | 3 | 5 | 24
EE | 2021-11-08 | 0 | 1 | 1 | 25
TT | 2021-11-08 | 0 | 8 | 8 | 25
FF | 2021-11-08 | 1 | 8 | 9 | 25
AA | 2021-11-08 | 0 | 2 | 2 | 25
QQ | 2021-11-08 | 6 | 24 | 30 | 25
FF | 2021-11-08 | 2 | 3 | 5 | 25
EE | 2021-11-19 | 0 | 1 | 1 | 26
TT | 2021-11-19 | 0 | 8 | 8 | 26
FF | 2021-11-19 | 1 | 8 | 9 | 26
AA | 2021-11-19 | 0 | 2 | 2 | 26
QQ | 2021-11-19 | 5 | 25 | 30 | 26
FF | 2021-11-19 | 2 | 3 | 5 | 26
EE | 2021-11-26 | 0 | 1 | 1 | 27
TT | 2021-11-26 | 0 | 8 | 8 | 27
FF | 2021-11-26 | 1 | 8 | 9 | 27
AA | 2021-11-26 | 0 | 2 | 2 | 27
QQ | 2021-11-26 | 19 | 25 | 44 | 27
FF | 2021-11-26 | 2 | 3 | 5 | 27
EE | 2021-12-03 | 0 | 1 | 1 | 28
TT | 2021-12-03 | 0 | 8 | 8 | 28
FF | 2021-12-03 | 0 | 9 | 9 | 28
AA | 2021-12-03 | 0 | 2 | 2 | 28
QQ | 2021-12-03 | 30 | 26 | 56 | 28
FF | 2021-12-03 | 0 | 5 | 5 | 28
EE | 2021-12-10 | 0 | 1 | 1 | 29
TT | 2021-12-10 | 0 | 8 | 8 | 29
FF | 2021-12-10 | 0 | 9 | 9 | 29
AA | 2021-12-10 | 0 | 2 | 2 | 29
QQ | 2021-12-10 | 26 | 38 | 64 | 29
FF | 2021-12-10 | 0 | 5 | 5 | 29
Formulas:
Date = [Date, row above]

## Quality Observation Report
Contractor Name | Date | OPEN | CLOSED | RAISED | Report No
EE | 2021-09-24 | 0 | 44 | 44 | 19
TT | 2021-09-24 | 0 | 51 | 51 | 19
FF | 2021-09-24 | 4 | 104 | 108 | 19
AA | 2021-09-24 | 0 | 8 | 8 | 19
QQ | 2021-09-24 | 16 | 56 | 72 | 19
FF | 2021-09-24 | 6 | 55 | 61 | 19
EE | 2021-10-01 | 0 | 44 | 44 | 20
TT | 2021-10-01 | 0 | 51 | 51 | 20
FF | 2021-10-01 | 4 | 104 | 108 | 20
AA | 2021-10-01 | 0 | 8 | 8 | 20
QQ | 2021-10-01 | 45 | 57 | 102 | 20
FF | 2021-10-01 | 6 | 63 | 69 | 20
EE | 2021-10-08 | 0 | 44 | 44 | 21
TT | 2021-10-08 | 0 | 51 | 51 | 21
FF | 2021-10-08 | 4 | 104 | 108 | 21
AA | 2021-10-08 | 0 | 8 | 8 | 21
QQ | 2021-10-08 | 56 | 72 | 128 | 21
FF | 2021-10-08 | 6 | 63 | 69 | 21
EE | 2021-10-21 | 0 | 44 | 44 | 23
TT | 2021-10-21 | 0 | 51 | 51 | 23
FF | 2021-10-21 | 4 | 104 | 108 | 23
AA | 2021-10-21 | 0 | 8 | 8 | 23
QQ | 2021-10-21 | 48 | 104 | 152 | 23
FF | 2021-10-21 | 53 | 76 | 129 | 23
EE | 2021-10-28 | 0 | 44 | 44 | 24
TT | 2021-10-28 | 0 | 51 | 51 | 24
FF | 2021-10-28 | 4 | 104 | 108 | 24
AA | 2021-10-28 | 0 | 8 | 8 | 24
QQ | 2021-10-28 | 22 | 146 | 164 | 24
FF | 2021-10-28 | 55 | 87 | 142 | 24
EE | 2021-11-08 | 0 | 44 | 44 | 25
TT | 2021-11-08 | 0 | 51 | 51 | 25
FF | 2021-11-08 | 4 | 104 | 108 | 25
AA | 2021-11-08 | 0 | 8 | 8 | 25
QQ | 2021-11-08 | 24 | 152 | 176 | 25
FF | 2021-11-08 | 55 | 87 | 142 | 25
EE | 2021-11-19 | 0 | 44 | 44 | 26
TT | 2021-11-19 | 0 | 51 | 51 | 26
FF | 2021-11-19 | 4 | 104 | 108 | 26
AA | 2021-11-19 | 0 | 8 | 8 | 26
QQ | 2021-11-19 | 13 | 163 | 176 | 26
FF | 2021-11-19 | 40 | 102 | 142 | 26
EE | 2021-11-26 | 0 | 44 | 44 | 27
TT | 2021-11-26 | 0 | 51 | 51 | 27
FF | 2021-11-26 | 4 | 104 | 108 | 27
AA | 2021-11-26 | 0 | 8 | 8 | 27
QQ | 2021-11-26 | 20 | 189 | 209 | 27
FF | 2021-11-26 | 40 | 102 | 142 | 27
EE | 2021-12-03 | 0 | 44 | 44 | 28
TT | 2021-12-03 | 0 | 51 | 51 | 28
FF | 2021-12-03 | 0 | 108 | 108 | 28
AA | 2021-12-03 | 0 | 8 | 8 | 28
QQ | 2021-12-03 | 21 | 189 | 210 | 28
FF | 2021-12-03 | 11 | 131 | 142 | 28
EE | 2021-12-10 | 0 | 44 | 44 | 29
TT | 2021-12-10 | 0 | 51 | 51 | 29
FF | 2021-12-10 | 0 | 108 | 108 | 29
AA | 2021-12-10 | 0 | 8 | 8 | 29
QQ | 2021-12-10 | 18 | 200 | 218 | 29
FF | 2021-12-10 | 11 | 131 | 142 | 29
Formulas:
Date = [Date, row above]

## Work Method Statement
Contractor Name | Date | Submitted | Approved | Pending | Report No
EE | 2021-09-24 | 8 | 8 | 0 | 19
TT | 2021-09-24 | 5 | 5 | 0 | 19
FF | 2021-09-24 | 3 | 3 | 0 | 19
AA | 2021-09-24 | 42 | 20 | 22 | 19
QQ | 2021-09-24 | 7 | 7 | 0 | 19
EE | 2021-10-01 | 8 | 8 | 0 | 20
TT | 2021-10-01 | 5 | 5 | 0 | 20
FF | 2021-10-01 | 3 | 3 | 0 | 20
AA | 2021-10-01 | 55 | 24 | 31 | 20
QQ | 2021-10-01 | 7 | 7 | 0 | 20
EE | 2021-10-08 | 8 | 8 | 0 | 21
TT | 2021-10-08 | 5 | 5 | 0 | 21
FF | 2021-10-08 | 3 | 3 | 0 | 21
AA | 2021-10-08 | 56 | 24 | 32 | 21
QQ | 2021-10-08 | 7 | 7 | 0 | 21
EE | 2021-10-21 | 8 | 8 | 0 | 23
TT | 2021-10-21 | 5 | 5 | 0 | 23
FF | 2021-10-21 | 3 | 3 | 0 | 23
AA | 2021-10-21 | 58 | 26 | 32 | 23
QQ | 2021-10-21 | 7 | 7 | 0 | 23
EE | 2021-10-28 | 8 | 8 | 0 | 24
TT | 2021-10-28 | 5 | 5 | 0 | 24
FF | 2021-10-28 | 3 | 3 | 0 | 24
AA | 2021-10-28 | 58 | 26 | 32 | 24
QQ | 2021-10-28 | 7 | 7 | 0 | 24
EE | 2021-11-08 | 8 | 8 | 0 | 25
TT | 2021-11-08 | 5 | 5 | 0 | 25
FF | 2021-11-08 | 3 | 3 | 0 | 25
AA | 2021-11-08 | 58 | 26 | 32 | 25
QQ | 2021-11-08 | 7 | 7 | 0 | 25
EE | 2021-11-19 | 8 | 8 | 0 | 26
TT | 2021-11-19 | 5 | 5 | 0 | 26
FF | 2021-11-19 | 3 | 3 | 0 | 26
AA | 2021-11-19 | 58 | 26 | 32 | 26
QQ | 2021-11-19 | 7 | 7 | 0 | 26
EE | 2021-11-26 | 5 | 5 | 0 | 27
TT | 2021-11-26 | 8 | 8 | 0 | 27
FF | 2021-11-26 | 3 | 3 | 0 | 27
AA | 2021-11-26 | 66 | 27 | 39 | 27
QQ | 2021-11-26 | 7 | 7 | 0 | 27
EE | 2021-12-03 | 5 | 5 | 0 | 28
TT | 2021-12-03 | 8 | 8 | 0 | 28
FF | 2021-12-03 | 3 | 3 | 0 | 28
AA | 2021-12-03 | 66 | 29 | 37 | 28
QQ | 2021-12-03 | 8 | 7 | 1 | 28
EE | 2021-12-10 | 5 | 5 | 0 | 29
TT | 2021-12-10 | 8 | 8 | 0 | 29
FF | 2021-12-10 | 3 | 3 | 0 | 29
AA | 2021-12-10 | 70 | 32 | 38 | 29
QQ | 2021-12-10 | 8 | 0 | 0 | 29
Formulas:
Date = [Date, row above]

## Weekly Cube Test Summary
Activity Name | Date | 7 Days | 28 days | Report No
Substation | 2021-09-24 | 1 | 0 | 19
HSD Building | 2021-09-24 | 0 | 0 | 19
DG Building | 2021-09-24 | 0 | 1 | 19
Substation | 2021-10-01 | 1 | 5 | 20
HSD Building | 2021-10-01 | 0 | 1 | 20
DG Building | 2021-10-01 | 0 | 0 | 20
Substation | 2021-10-08 | 3 | 0 | 21
WTP | 2021-10-08 | 4 | 0 | 21
Substation | 2021-10-21 | 0 | 0 | 23
Main Building | 2021-10-21 | 1 | 3 | 23
DG Building | 2021-10-21 | 6 | 1 | 23
WTP | 2021-10-21 | 0 | 0 | 23
Substation | 2021-10-28 | 0 | 0 | 24
Main Building | 2021-10-28 | 4 | 1 | 24
DG Building | 2021-10-28 | 0 | 4 | 24
WTP | 2021-10-28 | 1 | 4 | 24
Substation | 2021-11-08 | 0 | 0 | 25
Main Building | 2021-11-08 | 0 | 4 | 25
DG Building | 2021-11-08 | 0 | 0 | 25
WTP | 2021-11-08 | 0 | 4 | 25
Substation | 2021-11-19 | 0 | 0 | 26
Main Building | 2021-11-19 | 0 | 4 | 26
DG Building | 2021-11-19 | 0 | 0 | 26
WTP | 2021-11-19 | 0 | 3 | 26
Substation | 2021-11-26 | 1 | 0 | 27
Main Building | 2021-11-26 | 0 | 3 | 27
DG Building | 2021-11-26 | 0 | 0 | 27
WTP | 2021-11-26 | 0 | 0 | 27
Substation | 2021-12-03 | 0 | 0 | 28
Main Building | 2021-12-03 | 0 | 0 | 28
DG Building | 2021-12-03 | 0 | 4 | 28
WTP | 2021-12-03 | 0 | 0 | 28
Substation | 2021-12-10 | 0 | 2 | 29
Main Building | 2021-12-10 | 0 | 0 | 29
DG Building | 2021-12-10 | 0 | 0 | 29
WTP | 2021-12-10 | 0 | 2 | 29

## Quality -Observation tracker (hidden)
S.N | Observation Details | Location | Current Status | Responsible for action | Proposed corrective action by Gleeds | Actual corrective action taken | Date of issue by gleeds | Date of action taken | Report No
1 | Cracks wider than 3mm are being developed horizontally along the boundary wall | East side Boundary wall | OPEN | ACX | It must be inspected & necessary remedies to be recommended by a structural professional. | NA | 2021-07-10
|  |  | CLOSE |  | ACX should take corrective action accordingly
2 | Column starters must be completed before backfilling | Substation building | OPEN | ACX | Should be done as recommended | Proper shuttering has been done as per drawing | 2021-07-30 | 2021-08-05
3 | Wall starters were full of touch ups | Cable trench – Substation building | CLOSE | ACX | Must provide the cube strength test | Rectification done as per the approved methodology | 2021-07-30 | 2021-08-04
4 | Repeatedly observed backfilled materials with lot of boulders | HSD Building | OPEN | ACX | ACX should take the necessary actions as they have committed earlier | NA | 2021-07-30
5 | Wall concrete surfaces embedded with cotton wastes | HSD Building | CLOSE | ACX | Use an appropriate method to rectify it | Embedded cotton has been removed completely before shuttering | 2021-07-30 | 2021-08-06

## MIR Summary
Activity Name | MIR Last Week Submitted | MIR This Week Submitted | Date | Report No
Steel | 44 |  | 2021-09-24 | 19
Concrete | 6 |  | 2021-09-24 | 19
Anchor Bolt | 2 |  | 2021-09-24 | 19
Pentonite | 4 |  | 2021-09-24 | 19
Cover block | 6 |  | 2021-09-24 | 19
Binding wire | 4 |  | 2021-09-24 | 19
Welding rod | 3 |  | 2021-09-24 | 19
Geo fabric | 1 |  | 2021-09-24 | 19
HDPE pipe | 1 |  | 2021-09-24 | 19
Template | 2 |  | 2021-09-24 | 19
Soil | 2 |  | 2021-09-24 | 19
Anti termite chemical | 1 |  | 2021-09-24 | 19
LDPE Sheet | 1 |  | 2021-09-24 | 19
Structural Steel | 132 | 6 | 2021-09-24 | 19
Shuttering Oil | 2 |  | 2021-09-24 | 19
Farm Work | 3 |  | 2021-09-24 | 19
Admixture | 1 |  | 2021-09-24 | 19
Fastners | 2 |  | 2021-09-24 | 19
water proofing | 4 |  | 2021-09-24 | 19
EPW PIPE | 1 |  | 2021-09-24 | 19
Curing Chemical | 1 |  | 2021-09-24 | 19
AAC Block | 4 | 3 | 2021-09-24 | 19
GI Class c Pipe | 4 | 2 | 2021-09-24 | 19
Manual balancing Valve | 1 |  | 2021-09-24 | 19
Ms pipeline | 1 |  | 2021-09-24 | 19
Rock wool | 2 | 0 | 2021-09-24 | 19
Partition | 2 | 3 | 2021-09-24 | 19
ELV Equipment | 1 | 1 | 2021-09-24 | 19
Vermiculite Painting | 5 |  | 2021-09-24 | 19
Steel | 44 |  | 2021-10-01 | 20
Concrete | 6 |  | 2021-10-01 | 20
Anchor Bolt | 2 |  | 2021-10-01 | 20
Pentonite | 4 |  | 2021-10-01 | 20
Cover block | 6 |  | 2021-10-01 | 20
Binding wire | 4 |  | 2021-10-01 | 20
Welding rod | 3 |  | 2021-10-01 | 20
Geo fabric | 1 |  | 2021-10-01 | 20
HDPE pipe | 1 |  | 2021-10-01 | 20
Template | 2 |  | 2021-10-01 | 20
Soil | 2 |  | 2021-10-01 | 20
Anti termite chemical | 1 |  | 2021-10-01 | 20
LDPE Sheet | 1 |  | 2021-10-01 | 20
Structural Steel | 138 | 4 | 2021-10-01 | 20
Shuttering Oil | 2 |  | 2021-10-01 | 20
Farm Work | 3 |  | 2021-10-01 | 20
Admixture | 1 |  | 2021-10-01 | 20
Fastners | 2 |  | 2021-10-01 | 20
water proofing | 4 |  | 2021-10-01 | 20
EPW PIPE | 1 |  | 2021-10-01 | 20
Curing Chemical | 1 |  | 2021-10-01 | 20
AAC Block | 7 | 16 | 2021-10-01 | 20
GI Class c Pipe | 6 | 0 | 2021-10-01 | 20
Manual balancing Valve | 1 |  | 2021-10-01 | 20
Ms pipeline | 1 |  | 2021-10-01 | 20
Rock wool | 2 | 0 | 2021-10-01 | 20
Partition | 5 | 3 | 2021-10-01 | 20
ELV Equipment | 2 | 1 | 2021-10-01 | 20
Vermiculite Painting | 5
Steel | 44 |  | 2021-10-08 | 21
Concrete | 6 |  | 2021-10-08 | 21
Anchor Bolt | 2 |  | 2021-10-08 | 21
Pentonite | 4 |  | 2021-10-08 | 21
Cover block | 6 |  | 2021-10-08 | 21
Binding wire | 4 |  | 2021-10-08 | 21
Welding rod | 3 |  | 2021-10-08 | 21
Geo fabric | 1 |  | 2021-10-08 | 21
HDPE pipe | 1 |  | 2021-10-08 | 21
Template | 2 |  | 2021-10-08 | 21
Soil | 2 |  | 2021-10-08 | 21
Anti termite chemical | 1 |  | 2021-10-08 | 21
LDPE Sheet | 1 |  | 2021-10-08 | 21
Structural Steel | 142 | 19 | 2021-10-08 | 21
Shuttering Oil | 2 |  | 2021-10-08 | 21
Farm Work | 3 |  | 2021-10-08 | 21
Admixture | 1 |  | 2021-10-08 | 21
Fastners | 2 |  | 2021-10-08 | 21
water proofing | 4 |  | 2021-10-08 | 21
EPW PIPE | 1 |  | 2021-10-08 | 21
Curing Chemical | 1 |  | 2021-10-08 | 21
AAC Block | 7 |  | 2021-10-08 | 21
GI Class c Pipe | 23 |  | 2021-10-08 | 21
Manual balancing Valve | 1 |  | 2021-10-08 | 21
Ms pipeline | 1 |  | 2021-10-08 | 21
Rock wool | 2 |  | 2021-10-08 | 21
Partition | 5 |  | 2021-10-08 | 21
ELV Equipment | 3 |  | 2021-10-08 | 21
Vermiculite Painting | 5 |  | 2021-10-08 | 21
Civil | 89 | 4 | 2021-10-21 | 23
Finishes | 24 | 4 | 2021-10-21 | 23
Electrical | 18 |  | 2021-10-21 | 23
ELV | 17 | 5 | 2021-10-21 | 23
DG | 3 |  | 2021-10-21 | 23
GSS | 8 |  | 2021-10-21 | 23
FPS | 2 |  | 2021-10-21 | 23
HVAC | 19 |  | 2021-10-21 | 23
Strut Ceiling | 2 |  | 2021-10-21 | 23
PHE | 4 |  | 2021-10-21 | 23
Structural Steel | 140 | 25 | 2021-10-21 | 23
Civil | 93 | 3 | 2021-10-28 | 24
Finishes | 28 | 8 | 2021-10-28 | 24
Electrical | 18 | 1 | 2021-10-28 | 24
ELV | 25 |  | 2021-10-28 | 24
DG | 3 |  | 2021-10-28 | 24
GSS | 8 |  | 2021-10-28 | 24
FPS | 2 |  | 2021-10-28 | 24
HVAC | 19 | 6 | 2021-10-28 | 24
Strut Ceiling | 2 |  | 2021-10-28 | 24
PHE | 4 |  | 2021-10-28 | 24
Structural Steel | 165 | 0 | 2021-10-28 | 24
Civil | 96 |  | 2021-11-08 | 25
Finishes | 36 |  | 2021-11-08 | 25
Electrical | 19 | 3 | 2021-11-08 | 25
ELV | 25 | 3 | 2021-11-08 | 25
DG | 3 |  | 2021-11-08 | 25
GSS | 8 | 2 | 2021-11-08 | 25
FPS | 2 |  | 2021-11-08 | 25
HVAC | 25 | 3 | 2021-11-08 | 25
Strut Ceiling | 2 |  | 2021-11-08 | 25
PHE | 4 |  | 2021-11-08 | 25
Structural Steel | 165 | 0 | 2021-11-08 | 25
Civil | 96 | 3 | 2021-11-19 | 26
Finishes | 36 |  | 2021-11-19 | 26
Electrical | 22 |  | 2021-11-19 | 26
ELV | 28 |  | 2021-11-19 | 26
DG | 3 |  | 2021-11-19 | 26
GSS | 10 |  | 2021-11-19 | 26
FPS | 2 |  | 2021-11-19 | 26
HVAC | 28 |  | 2021-11-19 | 26
Strut Ceiling | 2 |  | 2021-11-19 | 26
PHE | 4 |  | 2021-11-19 | 26
Structural Steel | 165 | 2 | 2021-11-19 | 26
Civil | 122
Finishes | 45 | 3 | 2021-11-26 | 27
Electrical | 49 | 2 | 2021-11-26 | 27
ELV | 42 |  | 2021-11-26 | 27
DG | 3 | 1 | 2021-11-26 | 27
GSS | 10 |  | 2021-11-26 | 27
FPS | 5 |  | 2021-11-26 | 27
HVAC | 43 | 2 | 2021-11-26 | 27
Strut Ceiling | 2 |  | 2021-11-26 | 27
PHE | 5 |  | 2021-11-26 | 27
Structural Steel | 165 | 2 | 2021-11-26 | 27
Civil | 122 | 13 | 2021-12-03 | 28
Finishes | 48 | 0 | 2021-12-03 | 28
Electrical | 51 | 11 | 2021-12-03 | 28
ELV | 42 | 1 | 2021-12-03 | 28
DG | 4 | 0 | 2021-12-03 | 28
GSS | 10 | 6 | 2021-12-03 | 28
FPS | 5 | 4 | 2021-12-03 | 28
HVAC | 45 | 4 | 2021-12-03 | 28
Strut Ceiling | 2 | 1 | 2021-12-03 | 28
PHE | 5 | 2 | 2021-12-03 | 28
Structural Steel | 167 | 0 | 2021-12-03 | 28
Civil | 135 | 8 | 2021-12-10 | 29
Finishes | 48 | 0 | 2021-12-10 | 29
Electrical | 62 | 3 | 2021-12-10 | 29
ELV | 43 | 4 | 2021-12-10 | 29
DG | 4 | 0 | 2021-12-10 | 29
GSS | 16 | 0 | 2021-12-10 | 29
FPS | 9 | 1 | 2021-12-10 | 29
HVAC | 49 | 3 | 2021-12-10 | 29
Strut Ceiling | 3 | 0 | 2021-12-10 | 29
Solar | 0 | 1 | 2021-12-10 | 29
Formulas:
Date = [Date, row above]

## Status-2 (hidden)
STATUS
OPEN
CLOSE

## Contractor Name
Contractor Name
EE
TT
FF
QQ
XX
AA

## Quality Observation - Gleeds
Date | Open | Issued | Closed | Report No
2021-12-03 | 18 | 21 | 3 | 28
2021-12-10 | 12 | 17 | 5 | 29

## Quality Obser Cum - Gleeds
Date | Cum Open | Cum Issued | Cum Closed | Report No
2021-12-03 | 10 | 142 | 132 | 28
2021-12-03 | 28 | 163 | 135 | 29

## Status (hidden)
NCR Status
OPEN
CLOSED
RAISED