## Safety Summary
Description | Upto Last Week | This Week | Date | Report No
Men Hours Logged | 636515 | 49572 | 2021-09-24 | 19
Average no. of workforce | 6317 | 450 | 2021-09-24 | 19
No. Toolbox talk | 629 | 10 | 2021-09-24 | 19
No. of person inducted | 1178 | 47 | 2021-09-24 | 19
No. of person Re-inducted | 60 | 0 | 2021-09-24 | 19
Number of Safety Violation/Alert raised | 46 | 1 | 2021-09-24 | 19
Near- Misses | 8 | 0 | 2021-09-24 | 19
No. of First Aid Cases | 2 | 1 | 2021-09-24 | 19
No of Major Injuries | 0 | 0 | 2021-09-24 | 19
Men Hours Logged | 686087 | 49042 | 2021-10-01 | 20
Average no. of workforce | 6767 | 510 | 2021-10-01 | 20
No. Toolbox talk | 639 | 12 | 2021-10-01 | 20
No. of person inducted | 1225 | 58 | 2021-10-01 | 20
No. of person Re-inducted | 60 | 0 | 2021-10-01 | 20
Number of Safety Violation/Alert raised | 47 | 2 | 2021-10-01 | 20
Near- Misses | 8 | 0 | 2021-10-01 | 20
No. of First Aid Cases | 3 | 0 | 2021-10-01 | 20
No of Major Injuries | 0 | 0 | 2021-10-01 | 20
Men Hours Logged | 735129 | 41946 | 2021-10-08 | 21
Average no. of workforce | 7277 | 510 | 2021-10-08 | 21
No. Toolbox talk | 651 | 24 | 2021-10-08 | 21
No. of person inducted | 1283 | 58 | 2021-10-08 | 21
No. of person Re-inducted | 60 | 0 | 2021-10-08 | 21
Number of Safety Violation/Alert raised | 49 | 1 | 2021-10-08 | 21
Near- Misses | 8 | 0 | 2021-10-08 | 21
No. of First Aid Cases | 3 | 0 | 2021-10-08 | 21
No of Major Injuries | 0 | 0 | 2021-10-08 | 21
Men Hours Logged | 727503 | 36631 | 2021-10-15 | 22
Average no. of workforce | 6827 | 465 | 2021-10-15 | 22
No. Toolbox talk | 6851 | 15 | 2021-10-15 | 22
No. of person inducted | 1341 | 49 | 2021-10-15 | 22
Number of Safety Violation/Alert raised | 51 | 1 | 2021-10-15 | 22
Near- Misses | 8 | 1 | 2021-10-15 | 22
No. of First Aid Cases | 4 | 0 | 2021-10-15 | 22
Men Hours Logged | 764134 | 46806 | 2021-10-22 | 23
Average no. of workforce | 7292 | 525 | 2021-10-22 | 23
No. Toolbox talk | 6866 | 12 | 2021-10-22 | 23
No. of person inducted | 1390 | 120 | 2021-10-22 | 23
Number of Safety Violation/Alert raised | 52 | 1 | 2021-10-22 | 23
Near- Misses | 9 | 2 | 2021-10-22 | 23
No. of First Aid Cases | 4 | 1 | 2021-10-22 | 23
Men Hours Logged | 810940 | 44823 | 2021-10-29 | 24 | s
Average no. of workforce | 7817 | 475 | 2021-10-29 | 24
No. Toolbox talk | 6878 | 14 | 2021-10-29 | 24
No. of person inducted | 1510 | 81 | 2021-10-29 | 24
Number of Safety Violation/Alert raised | 53 | 0 | 2021-10-29 | 24
Near- Misses | 11 | 1 | 2021-10-29 | 24
No. of First Aid Cases | 5 | 1 | 2021-10-29 | 24
Men Hours Logged | 855763 | 51683 | 2021-11-08 | 25
Average no. of workforce | 8292 | 450 | 2021-11-08 | 25
No. Toolbox talk | 6895 | 21 | 2021-11-08 | 25
No. of person inducted | 1591 | 124 | 2021-11-08 | 25
Number of Safety Violation/Alert raised | 53 | 2 | 2021-11-08 | 25
Near- Misses | 12 | 1 | 2021-11-08 | 25
No. of First Aid Cases | 6 | 0 | 2021-11-08 | 25
Men Hours Logged | 938252 | 79719 | 2021-11-19 | 26
Average no. of workforce | 8742 | 450 | 2021-11-19 | 26
No. Toolbox talk | 6932 | 16 | 2021-11-19 | 26
No. of person inducted | 1715 | 203 | 2021-11-19 | 26
Number of Safety Violation/Alert raised | 55 | 3 | 2021-11-19 | 26
Near- Misses | 13 | 1 | 2021-11-19 | 26
No. of First Aid Cases | 6 | 0 | 2021-11-19 | 26
Men Hours Logged | 1017971 | 47422 | 2021-11-26 | 27
Average no. of workforce | 9192 | 450 | 2021-11-26 | 27
No. Toolbox talk | 6948 | 18 | 2021-11-26 | 27
No. of person inducted | 1918 | 145 | 2021-11-26 | 27
Number of Safety Violation/Alert raised | 58 | 3 | 2021-11-26 | 27
Near- Misses | 14 | 0 | 2021-11-26 | 27
No. of First Aid Cases | 6 | 0 | 2021-11-26 | 27
Men Hours Logged | 1065393 | 56094 | 2021-12-03 | 28
Average no. of workforce | 9642 | 530 | 2021-12-03 | 28
No. Toolbox talk | 761 | 20 | 2021-12-03 | 28
No. of person inducted | 2071 | 191 | 2021-12-03 | 28
Number of Safety Violation/Alert raised | 61 | 3 | 2021-12-03 | 28
Near- Misses | 14 | 2 | 2021-12-03 | 28
No. of First Aid Cases | 6 | 0 | 2021-12-03 | 28
Men Hours Logged | 1121487 | 67936 | 2021-12-10 | 29
Average no. of workforce | 10172 | 550 | 2021-12-10 | 29
No. Toolbox talk | 781 | 18 | 2021-12-10 | 29
No. of person inducted | 2122 | 51 | 2021-12-10 | 29
Number of Safety Violation/Alert raised | 67 | 4 | 2021-12-10 | 29
Near- Misses | 16 | 2 | 2021-12-10 | 29
No. of First Aid Cases | 7 | 0 | 2021-12-10 | 29
Formulas:
Date = [Date, row above]

## HSE Observation Report (hidden)
S.N | Observation Details | Location | Current Status | Responsible for action | Proposed corrective action by Gleeds | Actual corrective action taken | Date of issue by Gleeds | Date of action taken
1 | Phase 2 area materials stacking was very poor. Areas not barricaded. Water logging, no guided pedestrian walkways available. | Phase 2 Area | OPEN | ACX | Material stacking are to be properly barricaded. | NA | 2021-07-16
2 | Unused materials are dumped in the area. |  | CLOSE |  | Relevant sign boards to be displayed.
3 |  |  | CLOSE |  | Guided pedestrian walkways to be identified and demarked.
4 | Observed, water logging and leak in the workmen toile area resulting in algae formation and place for mosquito breeding. | L&W site office | CLOSE | ACX | Proper hygiene to be maintained in the workmen toilet area. Water logging to be cleared and leaks to be arrested. | NA | 2021-07-16
5 | Driveways identified are filled with slush and in an unsafe condition at multiple locations around the site. | Multiple locations | OPEN | ACX | Driveways to be cleared from slush and appropriate signboards to be displayed in the locations. | NA | 2021-07-16
6 | No caution/warning signs observed in the area.
7 | Speed limits signs were missing |  |  |  | Day today inspections to be done and as a monsoon precautions water ways to be made for the rainwater to flow and prevent logging in the driveways.

## Status (hidden)
Status
OPEN
CLOSE

## Date (hidden)
Date
2019-01-01
2019-01-02
2019-01-03
2019-01-04
2019-01-05
2019-01-06
2019-01-07
2019-01-08
2019-01-09
2019-01-10
2019-01-11
2019-01-12
2019-01-13
2019-01-14
2019-01-15
2019-01-16
2019-01-17
2019-01-18
2019-01-19
2019-01-20
2019-01-21
2019-01-22
2019-01-23
2019-01-24
2019-01-25
2019-01-26
2019-01-27
2019-01-28
2019-01-29
2019-01-30
2019-01-31
2019-02-01
2019-02-02
2019-02-03
2019-02-04
2019-02-05
2019-02-06
2019-02-07
2019-02-08
2019-02-09
2019-02-10
2019-02-11
2019-02-12
2019-02-13
2019-02-14
2019-02-15
2019-02-16
2019-02-17
2019-02-18
2019-02-19
2019-02-20
2019-02-21
2019-02-22
2019-02-23
2019-02-24
2019-02-25
2019-02-26
2019-02-27
2019-02-28
2019-03-01
2019-03-02
2019-03-03
2019-03-04
2019-03-05
2019-03-06
2019-03-07
2019-03-08
2019-03-09
2019-03-10
2019-03-11
2019-03-12
2019-03-13
2019-03-14
2019-03-15
2019-03-16
2019-03-17
2019-03-18
2019-03-19
2019-03-20
2019-03-21
2019-03-22
2019-03-23
2019-03-24
2019-03-25
2019-03-26
2019-03-27
2019-03-28
2019-03-29
2019-03-30
2019-03-31
2019-04-01
2019-04-02
2019-04-03
2019-04-04
2019-04-05
2019-04-06
2019-04-07
2019-04-08
2019-04-09
2019-04-10
2019-04-11
2019-04-12
2019-04-13
2019-04-14
2019-04-15
2019-04-16
2019-04-17
2019-04-18
2019-04-19
2019-04-20
2019-04-21
2019-04-22
2019-04-23
2019-04-24
2019-04-25
2019-04-26
2019-04-27
2019-04-28
2019-04-29
2019-04-30
2019-05-01
2019-05-02
2019-05-03
2019-05-04
2019-05-05
2019-05-06
2019-05-07
2019-05-08
2019-05-09
2019-05-10
2019-05-11
2019-05-12
2019-05-13
2019-05-14
2019-05-15
2019-05-16
2019-05-17
2019-05-18
2019-05-19
2019-05-20
2019-05-21
2019-05-22
2019-05-23
2019-05-24
2019-05-25
2019-05-26
2019-05-27
2019-05-28
2019-05-29
2019-05-30
2019-05-31
2019-06-01
2019-06-02
2019-06-03
2019-06-04
2019-06-05
2019-06-06
2019-06-07
2019-06-08
2019-06-09
2019-06-10
2019-06-11
2019-06-12
2019-06-13
2019-06-14
2019-06-15
2019-06-16
2019-06-17
2019-06-18
2019-06-19
2019-06-20
2019-06-21
2019-06-22
2019-06-23
2019-06-24
2019-06-25
2019-06-26
2019-06-27
2019-06-28
2019-06-29
2019-06-30
2019-07-01
2019-07-02
2019-07-03
2019-07-04
2019-07-05
2019-07-06
2019-07-07
2019-07-08
2019-07-09
2019-07-10
2019-07-11
2019-07-12
2019-07-13
2019-07-14
2019-07-15
2019-07-16
2019-07-17
2019-07-18
2019-07-19
2019-07-20
2019-07-21
2019-07-22
2019-07-23
2019-07-24
2019-07-25
2019-07-26
2019-07-27
2019-07-28
2019-07-29
2019-07-30
2019-07-31
2019-08-01
2019-08-02
2019-08-03
2019-08-04
2019-08-05
2019-08-06
2019-08-07
2019-08-08
2019-08-09
2019-08-10
2019-08-11
2019-08-12
2019-08-13
2019-08-14
2019-08-15
2019-08-16
2019-08-17
2019-08-18
2019-08-19
2019-08-20
2019-08-21
2019-08-22
2019-08-23
2019-08-24
2019-08-25
2019-08-26
2019-08-27
2019-08-28
2019-08-29
2019-08-30
2019-08-31
2019-09-01
2019-09-02
2019-09-03
2019-09-04
2019-09-05
2019-09-06
2019-09-07
2019-09-08
2019-09-09
2019-09-10
2019-09-11
2019-09-12
2019-09-13
2019-09-14
2019-09-15
2019-09-16
2019-09-17
2019-09-18
2019-09-19
2019-09-20
2019-09-21
2019-09-22
2019-09-23
2019-09-24
2019-09-25
2019-09-26
2019-09-27
2019-09-28
2019-09-29
2019-09-30
2019-10-01
2019-10-02
2019-10-03
2019-10-04
2019-10-05
2019-10-06
2019-10-07
2019-10-08
2019-10-09
2019-10-10
2019-10-11
2019-10-12
2019-10-13
2019-10-14
2019-10-15
2019-10-16
2019-10-17
2019-10-18
2019-10-19
2019-10-20
2019-10-21
2019-10-22
2019-10-23
2019-10-24
2019-10-25
2019-10-26
2019-10-27
2019-10-28
2019-10-29
2019-10-30
2019-10-31
2019-11-01
2019-11-02
2019-11-03
2019-11-04
2019-11-05
2019-11-06
2019-11-07
2019-11-08
2019-11-09
2019-11-10
2019-11-11
2019-11-12
2019-11-13
2019-11-14
2019-11-15
2019-11-16
2019-11-17
2019-11-18
2019-11-19
2019-11-20
2019-11-21
2019-11-22
2019-11-23
2019-11-24
2019-11-25
2019-11-26
2019-11-27
2019-11-28
2019-11-29
2019-11-30
2019-12-01
2019-12-02
2019-12-03
2019-12-04
2019-12-05
2019-12-06
2019-12-07
2019-12-08
2019-12-09
2019-12-10
2019-12-11
2019-12-12
2019-12-13
2019-12-14
2019-12-15
2019-12-16
2019-12-17
2019-12-18
2019-12-19
2019-12-20
2019-12-21
2019-12-22
2019-12-23
2019-12-24
2019-12-25
2019-12-26
2019-12-27
2019-12-28
2019-12-29
2019-12-30
2019-12-31
2020-01-01
2020-01-02
2020-01-03
2020-01-04
2020-01-05
2020-01-06
2020-01-07
2020-01-08
2020-01-09
2020-01-10
2020-01-11
2020-01-12
2020-01-13
2020-01-14
2020-01-15
2020-01-16
2020-01-17
2020-01-18
2020-01-19
2020-01-20
2020-01-21
2020-01-22
2020-01-23
2020-01-24
2020-01-25
2020-01-26
2020-01-27
2020-01-28
2020-01-29
2020-01-30
2020-01-31
2020-02-01
2020-02-02
2020-02-03
2020-02-04
2020-02-05
2020-02-06
2020-02-07
2020-02-08
2020-02-09
2020-02-10
2020-02-11
2020-02-12
2020-02-13
2020-02-14
2020-02-15
2020-02-16
2020-02-17
2020-02-18
2020-02-19
2020-02-20
2020-02-21
2020-02-22
2020-02-23
2020-02-24
2020-02-25
2020-02-26
2020-02-27
2020-02-28
2020-02-29
2020-03-01
2020-03-02
2020-03-03
2020-03-04
2020-03-05
2020-03-06
2020-03-07
2020-03-08
2020-03-09
2020-03-10
2020-03-11
2020-03-12
2020-03-13
2020-03-14
2020-03-15
2020-03-16
2020-03-17
2020-03-18
2020-03-19
2020-03-20
2020-03-21
2020-03-22
2020-03-23
2020-03-24
2020-03-25
2020-03-26
2020-03-27
2020-03-28
2020-03-29
2020-03-30
2020-03-31
2020-04-01
2020-04-02
2020-04-03
2020-04-04
2020-04-05
2020-04-06
2020-04-07
2020-04-08
2020-04-09
2020-04-10
2020-04-11
2020-04-12
2020-04-13
2020-04-14
2020-04-15
2020-04-16
2020-04-17
2020-04-18
2020-04-19
2020-04-20
2020-04-21
2020-04-22
2020-04-23
2020-04-24
2020-04-25
2020-04-26
2020-04-27
2020-04-28
2020-04-29
2020-04-30
2020-05-01
2020-05-02
2020-05-03
2020-05-04
2020-05-05
2020-05-06
2020-05-07
2020-05-08
2020-05-09
2020-05-10
2020-05-11
2020-05-12
2020-05-13
2020-05-14
2020-05-15
2020-05-16
2020-05-17
2020-05-18
2020-05-19
2020-05-20
2020-05-21
2020-05-22
2020-05-23
2020-05-24
2020-05-25
2020-05-26
2020-05-27
2020-05-28
2020-05-29
2020-05-30
2020-05-31
2020-06-01
2020-06-02
2020-06-03
2020-06-04
2020-06-05
2020-06-06
2020-06-07
2020-06-08
2020-06-09
2020-06-10
2020-06-11
2020-06-12
2020-06-13
2020-06-14
2020-06-15
2020-06-16
2020-06-17
2020-06-18
2020-06-19
2020-06-20
2020-06-21
2020-06-22
2020-06-23
2020-06-24
2020-06-25
2020-06-26
2020-06-27
2020-06-28
2020-06-29
2020-06-30
2020-07-01
2020-07-02
2020-07-03
2020-07-04
2020-07-05
2020-07-06
2020-07-07
2020-07-08
2020-07-09
2020-07-10
2020-07-11
2020-07-12
2020-07-13
2020-07-14
2020-07-15
2020-07-16
2020-07-17
2020-07-18
2020-07-19
2020-07-20
2020-07-21
2020-07-22
2020-07-23
2020-07-24
2020-07-25
2020-07-26
2020-07-27
2020-07-28
2020-07-29
2020-07-30
2020-07-31
2020-08-01
2020-08-02
2020-08-03
2020-08-04
2020-08-05
2020-08-06
2020-08-07
2020-08-08
2020-08-09
2020-08-10
2020-08-11
2020-08-12
2020-08-13
2020-08-14
2020-08-15
2020-08-16
2020-08-17
2020-08-18
2020-08-19
2020-08-20
2020-08-21
2020-08-22
2020-08-23
2020-08-24
2020-08-25
2020-08-26
2020-08-27
2020-08-28
2020-08-29
2020-08-30
2020-08-31
2020-09-01
2020-09-02
2020-09-03
2020-09-04
2020-09-05
2020-09-06
2020-09-07
2020-09-08
2020-09-09
2020-09-10
2020-09-11
2020-09-12
2020-09-13
2020-09-14
2020-09-15
2020-09-16
2020-09-17
2020-09-18
2020-09-19
2020-09-20
2020-09-21
2020-09-22
2020-09-23
2020-09-24
2020-09-25
2020-09-26
2020-09-27
2020-09-28
2020-09-29
2020-09-30
2020-10-01
2020-10-02
2020-10-03
2020-10-04
2020-10-05
2020-10-06
2020-10-07
2020-10-08
2020-10-09
2020-10-10
2020-10-11
2020-10-12
2020-10-13
2020-10-14
2020-10-15
2020-10-16
2020-10-17
2020-10-18
2020-10-19
2020-10-20
2020-10-21
2020-10-22
2020-10-23
2020-10-24
2020-10-25
2020-10-26
2020-10-27
2020-10-28
2020-10-29
2020-10-30
2020-10-31
2020-11-01
2020-11-02
2020-11-03
2020-11-04
2020-11-05
2020-11-06
2020-11-07
2020-11-08
2020-11-09
2020-11-10
2020-11-11
2020-11-12
2020-11-13
2020-11-14
2020-11-15
2020-11-16
2020-11-17
2020-11-18
2020-11-19
2020-11-20
2020-11-21
2020-11-22
2020-11-23
2020-11-24
2020-11-25
2020-11-26
2020-11-27
2020-11-28
2020-11-29
2020-11-30
2020-12-01
2020-12-02
2020-12-03
2020-12-04
2020-12-05
2020-12-06
2020-12-07
2020-12-08
2020-12-09
2020-12-10
2020-12-11
2020-12-12
2020-12-13
2020-12-14
2020-12-15
2020-12-16
2020-12-17
2020-12-18
2020-12-19
2020-12-20
2020-12-21
2020-12-22
2020-12-23
2020-12-24
2020-12-25
2020-12-26
2020-12-27
2020-12-28
2020-12-29
2020-12-30
2020-12-31
2021-01-01
2021-01-02
2021-01-03
2021-01-04
2021-01-05
2021-01-06
2021-01-07
2021-01-08
2021-01-09
2021-01-10
2021-01-11
2021-01-12
2021-01-13
2021-01-14
2021-01-15
2021-01-16
2021-01-17
2021-01-18
2021-01-19
2021-01-20
2021-01-21
2021-01-22
2021-01-23
2021-01-24
2021-01-25
2021-01-26
2021-01-27
2021-01-28
2021-01-29
2021-01-30
2021-01-31
2021-02-01
2021-02-02
2021-02-03
2021-02-04
2021-02-05
2021-02-06
2021-02-07
2021-02-08
2021-02-09
2021-02-10
2021-02-11
2021-02-12
2021-02-13
2021-02-14
2021-02-15
2021-02-16
2021-02-17
2021-02-18
2021-02-19
2021-02-20
2021-02-21
2021-02-22
2021-02-23
2021-02-24
2021-02-25
2021-02-26
2021-02-27
2021-02-28
2021-03-01
2021-03-02
2021-03-03
2021-03-04
2021-03-05
2021-03-06
2021-03-07
2021-03-08
2021-03-09
2021-03-10
2021-03-11
2021-03-12
2021-03-13
2021-03-14
2021-03-15
2021-03-16
2021-03-17
2021-03-18
2021-03-19
2021-03-20
2021-03-21
2021-03-22
2021-03-23
2021-03-24
2021-03-25
2021-03-26
2021-03-27
2021-03-28
2021-03-29
2021-03-30
2021-03-31
2021-04-01
2021-04-02
2021-04-03
2021-04-04
2021-04-05
2021-04-06
2021-04-07
2021-04-08
2021-04-09
2021-04-10
2021-04-11
2021-04-12
2021-04-13
2021-04-14
2021-04-15
2021-04-16
2021-04-17
2021-04-18
2021-04-19
2021-04-20
2021-04-21
2021-04-22
2021-04-23
2021-04-24
2021-04-25
2021-04-26
2021-04-27
2021-04-28
2021-04-29
2021-04-30
2021-05-01
2021-05-02
2021-05-03
2021-05-04
2021-05-05
2021-05-06
2021-05-07
2021-05-08
2021-05-09
2021-05-10
2021-05-11
2021-05-12
2021-05-13
2021-05-14
2021-05-15
2021-05-16
2021-05-17
2021-05-18
2021-05-19
2021-05-20
2021-05-21
2021-05-22
2021-05-23
2021-05-24
2021-05-25
2021-05-26
2021-05-27
2021-05-28
2021-05-29
2021-05-30
2021-05-31
2021-06-01
2021-06-02
2021-06-03
2021-06-04
2021-06-05
2021-06-06
2021-06-07
2021-06-08
2021-06-09
2021-06-10
2021-06-11
2021-06-12
2021-06-13
2021-06-14
2021-06-15
2021-06-16
2021-06-17
2021-06-18
2021-06-19
2021-06-20
2021-06-21
2021-06-22
2021-06-23
2021-06-24
2021-06-25
2021-06-26
2021-06-27
2021-06-28
2021-06-29
2021-06-30
2021-07-01
2021-07-02
2021-07-03
2021-07-04
2021-07-05
2021-07-06
2021-07-07
2021-07-08
2021-07-09
2021-07-10
2021-07-11
2021-07-12
2021-07-13
2021-07-14
2021-07-15
2021-07-16
2021-07-17
2021-07-18
2021-07-19
2021-07-20
2021-07-21
2021-07-22
2021-07-23
2021-07-24
2021-07-25
2021-07-26
2021-07-27
2021-07-28
2021-07-29
2021-07-30
2021-07-31
2021-08-01
2021-08-02
2021-08-03
2021-08-04
2021-08-05
2021-08-06
2021-08-07
2021-08-08
2021-08-09
2021-08-10
2021-08-11
2021-08-12
2021-08-13
2021-08-14
2021-08-15
2021-08-16
2021-08-17
2021-08-18
2021-08-19
2021-08-20
2021-08-21
2021-08-22
2021-08-23
2021-08-24
2021-08-25
2021-08-26
2021-08-27
2021-08-28
2021-08-29
2021-08-30
2021-08-31
2021-09-01
2021-09-02
2021-09-03
2021-09-04
2021-09-05
2021-09-06
2021-09-07
2021-09-08
2021-09-09
2021-09-10
2021-09-11
2021-09-12
2021-09-13
2021-09-14
2021-09-15
2021-09-16
2021-09-17
2021-09-18
2021-09-19
2021-09-20
2021-09-21
2021-09-22
2021-09-23
2021-09-24
2021-09-25
2021-09-26
2021-09-27
2021-09-28
2021-09-29
2021-09-30
2021-10-01
2021-10-02
2021-10-03
2021-10-04
2021-10-05
2021-10-06
2021-10-07
2021-10-08
2021-10-09
2021-10-10
2021-10-11
2021-10-12
2021-10-13
2021-10-14
2021-10-15
2021-10-16
2021-10-17
2021-10-18
2021-10-19
2021-10-20
2021-10-21
2021-10-22
2021-10-23
2021-10-24
2021-10-25
2021-10-26
2021-10-27
2021-10-28
2021-10-29
2021-10-30
2021-10-31
2021-11-01
2021-11-02
2021-11-03
2021-11-04
2021-11-05
2021-11-06
2021-11-07
2021-11-08
2021-11-09
2021-11-10
2021-11-11
2021-11-12
2021-11-13
2021-11-14
2021-11-15
2021-11-16
2021-11-17
2021-11-18
2021-11-19
2021-11-20
2021-11-21
2021-11-22
2021-11-23
2021-11-24
2021-11-25
2021-11-26
2021-11-27
2021-11-28
2021-11-29
2021-11-30
2021-12-01
2021-12-02
2021-12-03
2021-12-04
2021-12-05
2021-12-06
2021-12-07
2021-12-08
2021-12-09
2021-12-10
2021-12-11
2021-12-12
2021-12-13
2021-12-14
2021-12-15
2021-12-16
2021-12-17
2021-12-18
2021-12-19
2021-12-20
2021-12-21
2021-12-22
2021-12-23
2021-12-24
2021-12-25
2021-12-26
2021-12-27
2021-12-28
2021-12-29
2021-12-30
2021-12-31
2022-01-01
2022-01-02
2022-01-03
2022-01-04
2022-01-05
2022-01-06
2022-01-07
2022-01-08
2022-01-09
2022-01-10
2022-01-11
2022-01-12
2022-01-13
2022-01-14
2022-01-15
2022-01-16
2022-01-17
2022-01-18
2022-01-19
2022-01-20
2022-01-21
2022-01-22
2022-01-23
2022-01-24
2022-01-25
2022-01-26
2022-01-27
2022-01-28
2022-01-29
2022-01-30
2022-01-31
2022-02-01
2022-02-02
2022-02-03
2022-02-04
2022-02-05
2022-02-06
2022-02-07
2022-02-08
2022-02-09
2022-02-10
2022-02-11
2022-02-12
2022-02-13
2022-02-14
2022-02-15
2022-02-16
2022-02-17
2022-02-18
2022-02-19
2022-02-20
2022-02-21
2022-02-22
2022-02-23
2022-02-24
2022-02-25
2022-02-26
2022-02-27
2022-02-28
2022-03-01
2022-03-02
2022-03-03
2022-03-04
2022-03-05
2022-03-06
2022-03-07
2022-03-08
2022-03-09
2022-03-10
2022-03-11
2022-03-12
2022-03-13
2022-03-14
2022-03-15
2022-03-16
2022-03-17
2022-03-18
2022-03-19
2022-03-20
2022-03-21
2022-03-22
2022-03-23
2022-03-24
2022-03-25
2022-03-26
2022-03-27
2022-03-28
2022-03-29
2022-03-30
2022-03-31
2022-04-01
2022-04-02
2022-04-03
2022-04-04
2022-04-05
2022-04-06
2022-04-07
2022-04-08
2022-04-09
2022-04-10
2022-04-11
2022-04-12
2022-04-13
2022-04-14
2022-04-15
2022-04-16
2022-04-17
2022-04-18
2022-04-19
2022-04-20
2022-04-21
2022-04-22
2022-04-23
2022-04-24
2022-04-25
2022-04-26
2022-04-27
2022-04-28
2022-04-29
2022-04-30
2022-05-01
2022-05-02
2022-05-03
2022-05-04
2022-05-05
2022-05-06
2022-05-07
2022-05-08
2022-05-09
2022-05-10
2022-05-11
2022-05-12
2022-05-13
2022-05-14
2022-05-15
2022-05-16
2022-05-17
2022-05-18
2022-05-19
2022-05-20
2022-05-21
2022-05-22
2022-05-23
2022-05-24
2022-05-25
2022-05-26
2022-05-27
2022-05-28
2022-05-29
2022-05-30
2022-05-31
2022-06-01
2022-06-02
2022-06-03
2022-06-04
2022-06-05
2022-06-06
2022-06-07
2022-06-08
2022-06-09
2022-06-10
2022-06-11
2022-06-12
2022-06-13
2022-06-14
2022-06-15
2022-06-16
2022-06-17
2022-06-18
2022-06-19
2022-06-20
2022-06-21
2022-06-22
2022-06-23
2022-06-24
2022-06-25
2022-06-26
2022-06-27
2022-06-28
2022-06-29
2022-06-30
2022-07-01
2022-07-02
2022-07-03
2022-07-04
2022-07-05
2022-07-06
2022-07-07
2022-07-08
2022-07-09
2022-07-10
2022-07-11
2022-07-12
2022-07-13
2022-07-14
2022-07-15
2022-07-16
2022-07-17
2022-07-18
2022-07-19
2022-07-20
2022-07-21
2022-07-22
2022-07-23
2022-07-24
2022-07-25
2022-07-26
2022-07-27
2022-07-28
2022-07-29
2022-07-30
2022-07-31
2022-08-01
2022-08-02
2022-08-03
2022-08-04
2022-08-05
2022-08-06
2022-08-07
2022-08-08
2022-08-09
2022-08-10
2022-08-11
2022-08-12
2022-08-13
2022-08-14
2022-08-15
2022-08-16
2022-08-17
2022-08-18
2022-08-19
2022-08-20
2022-08-21
2022-08-22
2022-08-23
2022-08-24
2022-08-25
2022-08-26
2022-08-27
2022-08-28
2022-08-29
2022-08-30
2022-08-31
2022-09-01
2022-09-02
2022-09-03
2022-09-04
2022-09-05
2022-09-06
2022-09-07
2022-09-08
2022-09-09
2022-09-10
2022-09-11
2022-09-12
2022-09-13
2022-09-14
2022-09-15
2022-09-16
2022-09-17
2022-09-18
2022-09-19
2022-09-20
2022-09-21
2022-09-22
2022-09-23
2022-09-24
2022-09-25
2022-09-26
2022-09-27
2022-09-28
2022-09-29
2022-09-30
2022-10-01
2022-10-02
2022-10-03
2022-10-04
2022-10-05
2022-10-06
2022-10-07
2022-10-08
2022-10-09
2022-10-10
2022-10-11
2022-10-12
2022-10-13
2022-10-14
2022-10-15
2022-10-16
2022-10-17
2022-10-18
2022-10-19
2022-10-20
2022-10-21
2022-10-22
2022-10-23
2022-10-24
2022-10-25
2022-10-26
2022-10-27
2022-10-28
2022-10-29
2022-10-30
2022-10-31
2022-11-01
2022-11-02
2022-11-03
2022-11-04
2022-11-05
2022-11-06
2022-11-07
2022-11-08
2022-11-09
2022-11-10
2022-11-11
2022-11-12
2022-11-13
2022-11-14
2022-11-15
2022-11-16
2022-11-17
2022-11-18
2022-11-19
2022-11-20
2022-11-21
2022-11-22
2022-11-23
2022-11-24
2022-11-25
2022-11-26
2022-11-27
2022-11-28
2022-11-29
2022-11-30
2022-12-01
2022-12-02
2022-12-03
2022-12-04
2022-12-05
2022-12-06
2022-12-07
2022-12-08
2022-12-09
2022-12-10
2022-12-11
2022-12-12
2022-12-13
2022-12-14
2022-12-15
2022-12-16
2022-12-17
2022-12-18
2022-12-19
2022-12-20
2022-12-21
2022-12-22
2022-12-23
2022-12-24
2022-12-25
2022-12-26
2022-12-27
2022-12-28
2022-12-29
2022-12-30
2022-12-31
2023-01-01
2023-01-02
2023-01-03
2023-01-04
2023-01-05
2023-01-06
2023-01-07
2023-01-08
2023-01-09
2023-01-10
2023-01-11
2023-01-12
2023-01-13
2023-01-14
2023-01-15
2023-01-16
2023-01-17
2023-01-18
2023-01-19
2023-01-20
2023-01-21
2023-01-22
2023-01-23
2023-01-24
2023-01-25
2023-01-26
2023-01-27
2023-01-28
2023-01-29
2023-01-30
2023-01-31
2023-02-01
2023-02-02
2023-02-03
2023-02-04
2023-02-05
2023-02-06
2023-02-07
2023-02-08
2023-02-09
2023-02-10
2023-02-11
2023-02-12
2023-02-13
2023-02-14
2023-02-15
2023-02-16
2023-02-17
2023-02-18
2023-02-19
2023-02-20
2023-02-21
2023-02-22
2023-02-23
2023-02-24
2023-02-25
2023-02-26
2023-02-27
2023-02-28
2023-03-01
2023-03-02
2023-03-03
2023-03-04
2023-03-05
2023-03-06
2023-03-07
2023-03-08
2023-03-09
2023-03-10
2023-03-11
2023-03-12
2023-03-13
2023-03-14
2023-03-15
2023-03-16
2023-03-17
2023-03-18
2023-03-19
2023-03-20
2023-03-21
2023-03-22
2023-03-23
2023-03-24
2023-03-25
2023-03-26
2023-03-27
2023-03-28
2023-03-29
2023-03-30
2023-03-31
2023-04-01
2023-04-02
2023-04-03
2023-04-04
2023-04-05
2023-04-06
2023-04-07
2023-04-08
2023-04-09
2023-04-10
2023-04-11
2023-04-12
2023-04-13
2023-04-14
2023-04-15
2023-04-16
2023-04-17
2023-04-18
2023-04-19
2023-04-20
2023-04-21
2023-04-22
2023-04-23
2023-04-24
2023-04-25
2023-04-26
2023-04-27
2023-04-28
2023-04-29
2023-04-30
2023-05-01
2023-05-02
2023-05-03
2023-05-04
2023-05-05
2023-05-06
2023-05-07
2023-05-08
2023-05-09
2023-05-10
2023-05-11
2023-05-12
2023-05-13
2023-05-14
2023-05-15
2023-05-16
2023-05-17
2023-05-18
2023-05-19
2023-05-20
2023-05-21
2023-05-22
2023-05-23
2023-05-24
2023-05-25
2023-05-26
2023-05-27
2023-05-28
2023-05-29
2023-05-30
2023-05-31
2023-06-01
2023-06-02
2023-06-03
2023-06-04
2023-06-05
2023-06-06
2023-06-07
2023-06-08
2023-06-09
2023-06-10
2023-06-11
2023-06-12
2023-06-13
2023-06-14
2023-06-15
2023-06-16
2023-06-17
2023-06-18
2023-06-19
2023-06-20
2023-06-21
2023-06-22
2023-06-23
2023-06-24
2023-06-25
2023-06-26
2023-06-27
2023-06-28
2023-06-29
2023-06-30
2023-07-01
2023-07-02
2023-07-03
2023-07-04
2023-07-05
2023-07-06
2023-07-07
2023-07-08
2023-07-09
2023-07-10
2023-07-11
2023-07-12
2023-07-13
2023-07-14
2023-07-15
2023-07-16
2023-07-17
2023-07-18
2023-07-19
2023-07-20
2023-07-21
2023-07-22
2023-07-23
2023-07-24
2023-07-25
2023-07-26
2023-07-27
2023-07-28
2023-07-29
2023-07-30
2023-07-31
2023-08-01
2023-08-02
2023-08-03
2023-08-04
2023-08-05
2023-08-06
2023-08-07
2023-08-08
2023-08-09
2023-08-10
2023-08-11
2023-08-12
2023-08-13
2023-08-14
2023-08-15
2023-08-16
2023-08-17
2023-08-18
2023-08-19
2023-08-20
2023-08-21
2023-08-22
2023-08-23
2023-08-24
2023-08-25
2023-08-26
2023-08-27
2023-08-28
2023-08-29
2023-08-30
2023-08-31
2023-09-01
2023-09-02
2023-09-03
2023-09-04
2023-09-05
2023-09-06
2023-09-07
2023-09-08
2023-09-09
2023-09-10
2023-09-11
2023-09-12
2023-09-13
2023-09-14
2023-09-15
2023-09-16
2023-09-17
2023-09-18
2023-09-19
2023-09-20
2023-09-21
2023-09-22
2023-09-23
2023-09-24
2023-09-25
2023-09-26
2023-09-27
2023-09-28
2023-09-29
2023-09-30
2023-10-01
2023-10-02
2023-10-03
2023-10-04
2023-10-05
2023-10-06
2023-10-07
2023-10-08
2023-10-09
2023-10-10
2023-10-11
2023-10-12
2023-10-13
2023-10-14
2023-10-15
2023-10-16
2023-10-17
2023-10-18
2023-10-19
2023-10-20
2023-10-21
2023-10-22
2023-10-23
2023-10-24
2023-10-25
2023-10-26
2023-10-27
2023-10-28
2023-10-29
2023-10-30
2023-10-31
2023-11-01
2023-11-02
2023-11-03
2023-11-04
2023-11-05
2023-11-06
2023-11-07
2023-11-08
2023-11-09
2023-11-10
2023-11-11
2023-11-12
2023-11-13
2023-11-14
2023-11-15
2023-11-16
2023-11-17
2023-11-18
2023-11-19
2023-11-20
2023-11-21
2023-11-22
2023-11-23
2023-11-24
2023-11-25
2023-11-26
2023-11-27
2023-11-28
2023-11-29
2023-11-30
2023-12-01
2023-12-02
2023-12-03
2023-12-04
2023-12-05
2023-12-06
2023-12-07
2023-12-08
2023-12-09
2023-12-10
2023-12-11
2023-12-12
2023-12-13
2023-12-14
2023-12-15
2023-12-16
2023-12-17
2023-12-18
2023-12-19
2023-12-20
2023-12-21
2023-12-22
2023-12-23
2023-12-24
2023-12-25
2023-12-26
2023-12-27
2023-12-28
2023-12-29
2023-12-30
2023-12-31
2024-01-01
2024-01-02
2024-01-03
2024-01-04
2024-01-05
2024-01-06
2024-01-07
2024-01-08
2024-01-09
2024-01-10
2024-01-11
2024-01-12
2024-01-13
2024-01-14
2024-01-15
2024-01-16
2024-01-17
2024-01-18
2024-01-19
2024-01-20
2024-01-21
2024-01-22
2024-01-23
2024-01-24
2024-01-25
2024-01-26
2024-01-27
2024-01-28
2024-01-29
2024-01-30
2024-01-31
2024-02-01
2024-02-02
2024-02-03
2024-02-04
2024-02-05
2024-02-06
2024-02-07
2024-02-08
2024-02-09
2024-02-10
2024-02-11
2024-02-12
2024-02-13
2024-02-14
2024-02-15
2024-02-16
2024-02-17
2024-02-18
2024-02-19
2024-02-20
2024-02-21
2024-02-22
2024-02-23
2024-02-24
2024-02-25
2024-02-26
2024-02-27
2024-02-28
2024-02-29
2024-03-01
2024-03-02
2024-03-03
2024-03-04
2024-03-05
2024-03-06
2024-03-07
2024-03-08
2024-03-09
2024-03-10
2024-03-11
2024-03-12
2024-03-13
2024-03-14
2024-03-15
2024-03-16
2024-03-17
2024-03-18
2024-03-19
2024-03-20
2024-03-21
2024-03-22
2024-03-23
2024-03-24
2024-03-25
2024-03-26
2024-03-27
2024-03-28
2024-03-29
2024-03-30
2024-03-31
2024-04-01
2024-04-02
2024-04-03
2024-04-04
2024-04-05
2024-04-06
2024-04-07
2024-04-08
2024-04-09
2024-04-10
2024-04-11
2024-04-12
2024-04-13
2024-04-14
2024-04-15
2024-04-16
2024-04-17
2024-04-18
2024-04-19
2024-04-20
2024-04-21
2024-04-22
2024-04-23
2024-04-24
2024-04-25
2024-04-26
2024-04-27
2024-04-28
2024-04-29
2024-04-30
2024-05-01
2024-05-02
2024-05-03
2024-05-04
2024-05-05
2024-05-06
2024-05-07
2024-05-08
2024-05-09
2024-05-10
2024-05-11
2024-05-12
2024-05-13
2024-05-14
2024-05-15
2024-05-16
2024-05-17
2024-05-18
2024-05-19
2024-05-20
2024-05-21
2024-05-22
2024-05-23
2024-05-24
2024-05-25
2024-05-26
2024-05-27
2024-05-28
2024-05-29
2024-05-30
2024-05-31
2024-06-01
2024-06-02
2024-06-03
2024-06-04
2024-06-05
2024-06-06
2024-06-07
2024-06-08
2024-06-09
2024-06-10
2024-06-11
2024-06-12
2024-06-13
2024-06-14
2024-06-15
2024-06-16
2024-06-17
2024-06-18
2024-06-19
2024-06-20
2024-06-21
2024-06-22
2024-06-23
2024-06-24
2024-06-25
2024-06-26
2024-06-27
2024-06-28
2024-06-29
2024-06-30
2024-07-01
2024-07-02
2024-07-03
2024-07-04
2024-07-05
2024-07-06
2024-07-07
2024-07-08
2024-07-09
2024-07-10
2024-07-11
2024-07-12
2024-07-13
2024-07-14
2024-07-15
2024-07-16
2024-07-17
2024-07-18
2024-07-19
2024-07-20
2024-07-21
2024-07-22
2024-07-23
2024-07-24
2024-07-25
2024-07-26
2024-07-27
2024-07-28
2024-07-29
2024-07-30
2024-07-31
2024-08-01
2024-08-02
2024-08-03
2024-08-04
2024-08-05
2024-08-06
2024-08-07
2024-08-08
2024-08-09
2024-08-10
2024-08-11
2024-08-12
2024-08-13
2024-08-14
2024-08-15
2024-08-16
2024-08-17
2024-08-18
2024-08-19
2024-08-20
2024-08-21
2024-08-22
2024-08-23
2024-08-24
2024-08-25
2024-08-26
2024-08-27
2024-08-28
2024-08-29
2024-08-30
2024-08-31
2024-09-01
2024-09-02
2024-09-03
2024-09-04
2024-09-05
2024-09-06
2024-09-07
2024-09-08
2024-09-09
2024-09-10
2024-09-11
2024-09-12
2024-09-13
2024-09-14
2024-09-15
2024-09-16
2024-09-17
2024-09-18
2024-09-19
2024-09-20
2024-09-21
2024-09-22
2024-09-23
2024-09-24
2024-09-25
2024-09-26
2024-09-27
2024-09-28
2024-09-29
2024-09-30
2024-10-01
2024-10-02
2024-10-03
2024-10-04
2024-10-05
2024-10-06
2024-10-07
2024-10-08
2024-10-09
2024-10-10
2024-10-11
2024-10-12
2024-10-13
2024-10-14
2024-10-15
2024-10-16
2024-10-17
2024-10-18
2024-10-19
2024-10-20
2024-10-21
2024-10-22
2024-10-23
2024-10-24
2024-10-25
2024-10-26
2024-10-27
2024-10-28
2024-10-29
2024-10-30
2024-10-31
2024-11-01
2024-11-02
2024-11-03
2024-11-04
2024-11-05
2024-11-06
2024-11-07
2024-11-08
2024-11-09
2024-11-10
2024-11-11
2024-11-12
2024-11-13
2024-11-14
2024-11-15
2024-11-16
2024-11-17
2024-11-18
2024-11-19
2024-11-20
2024-11-21
2024-11-22
2024-11-23
2024-11-24
2024-11-25
2024-11-26
2024-11-27
2024-11-28
2024-11-29
2024-11-30
2024-12-01
2024-12-02
2024-12-03
2024-12-04
2024-12-05
2024-12-06
2024-12-07
2024-12-08
2024-12-09
2024-12-10
2024-12-11
2024-12-12
2024-12-13
2024-12-14
2024-12-15
2024-12-16
2024-12-17
2024-12-18
2024-12-19
2024-12-20
2024-12-21
2024-12-22
2024-12-23
2024-12-24
2024-12-25
2024-12-26
2024-12-27
2024-12-28
2024-12-29
2024-12-30
2024-12-31
2025-01-01
2025-01-02
2025-01-03
2025-01-04
2025-01-05
2025-01-06
2025-01-07
2025-01-08
2025-01-09
2025-01-10
2025-01-11
2025-01-12
2025-01-13
2025-01-14
2025-01-15
2025-01-16
2025-01-17
2025-01-18
2025-01-19
2025-01-20
2025-01-21
2025-01-22
2025-01-23
2025-01-24
2025-01-25
2025-01-26
2025-01-27
2025-01-28
2025-01-29
2025-01-30
2025-01-31
2025-02-01
2025-02-02
2025-02-03
2025-02-04
2025-02-05
2025-02-06
2025-02-07
2025-02-08
2025-02-09
2025-02-10
2025-02-11
2025-02-12
2025-02-13
2025-02-14
2025-02-15
2025-02-16
2025-02-17
2025-02-18
2025-02-19
2025-02-20
2025-02-21
2025-02-22
2025-02-23
2025-02-24
2025-02-25
2025-02-26
2025-02-27
2025-02-28
2025-03-01
2025-03-02
2025-03-03
2025-03-04
2025-03-05
2025-03-06
2025-03-07
2025-03-08
2025-03-09
2025-03-10
2025-03-11
2025-03-12
2025-03-13
2025-03-14
2025-03-15
2025-03-16
2025-03-17
2025-03-18
2025-03-19
2025-03-20
2025-03-21
2025-03-22
2025-03-23
2025-03-24
2025-03-25
2025-03-26
2025-03-27
2025-03-28
2025-03-29
2025-03-30
2025-03-31
2025-04-01
2025-04-02
2025-04-03
2025-04-04
2025-04-05
2025-04-06
2025-04-07
2025-04-08
2025-04-09
2025-04-10
2025-04-11
2025-04-12
2025-04-13
2025-04-14
2025-04-15
2025-04-16
2025-04-17
2025-04-18
2025-04-19
2025-04-20
2025-04-21
2025-04-22
2025-04-23
2025-04-24
2025-04-25
2025-04-26
2025-04-27
2025-04-28
2025-04-29
2025-04-30
2025-05-01
2025-05-02
2025-05-03
2025-05-04
2025-05-05
2025-05-06
2025-05-07
2025-05-08
2025-05-09
2025-05-10
2025-05-11
2025-05-12
2025-05-13
2025-05-14
2025-05-15
2025-05-16
2025-05-17
2025-05-18
2025-05-19
2025-05-20
2025-05-21
2025-05-22
2025-05-23
2025-05-24
2025-05-25
2025-05-26
2025-05-27
2025-05-28
2025-05-29
2025-05-30
2025-05-31
2025-06-01
2025-06-02
2025-06-03
2025-06-04
2025-06-05
2025-06-06
2025-06-07
2025-06-08
2025-06-09
2025-06-10
2025-06-11
2025-06-12
2025-06-13
2025-06-14
2025-06-15
2025-06-16
2025-06-17
2025-06-18
2025-06-19
2025-06-20
2025-06-21
2025-06-22
2025-06-23
2025-06-24
2025-06-25
2025-06-26
2025-06-27
2025-06-28
2025-06-29
2025-06-30
2025-07-01
2025-07-02
2025-07-03
2025-07-04
2025-07-05
2025-07-06
2025-07-07
2025-07-08
2025-07-09
2025-07-10
2025-07-11
2025-07-12
2025-07-13
2025-07-14
2025-07-15
2025-07-16
2025-07-17
2025-07-18
2025-07-19
2025-07-20
2025-07-21
2025-07-22
2025-07-23
2025-07-24
2025-07-25
2025-07-26
2025-07-27
2025-07-28
2025-07-29
2025-07-30
2025-07-31
2025-08-01
2025-08-02
2025-08-03
2025-08-04
2025-08-05
2025-08-06
2025-08-07
2025-08-08
2025-08-09
2025-08-10
2025-08-11
2025-08-12
2025-08-13
2025-08-14
2025-08-15
2025-08-16
2025-08-17
2025-08-18
2025-08-19
2025-08-20
2025-08-21
2025-08-22
2025-08-23
2025-08-24
2025-08-25
2025-08-26
2025-08-27
2025-08-28
2025-08-29
2025-08-30
2025-08-31
2025-09-01
2025-09-02
2025-09-03
2025-09-04
2025-09-05
2025-09-06
2025-09-07
2025-09-08
2025-09-09
2025-09-10
2025-09-11
2025-09-12
2025-09-13
2025-09-14
2025-09-15
2025-09-16
2025-09-17
2025-09-18
2025-09-19
2025-09-20
2025-09-21
2025-09-22
2025-09-23
2025-09-24
2025-09-25
2025-09-26
2025-09-27
2025-09-28
2025-09-29
2025-09-30
2025-10-01
2025-10-02
2025-10-03
2025-10-04
2025-10-05
2025-10-06
2025-10-07
2025-10-08
2025-10-09
2025-10-10
2025-10-11
2025-10-12
2025-10-13
2025-10-14
2025-10-15
2025-10-16
2025-10-17
2025-10-18
2025-10-19
2025-10-20
2025-10-21
2025-10-22
2025-10-23
2025-10-24
2025-10-25
2025-10-26
2025-10-27
2025-10-28
2025-10-29
2025-10-30
2025-10-31
2025-11-01
2025-11-02
2025-11-03
2025-11-04
2025-11-05
2025-11-06
2025-11-07
2025-11-08
2025-11-09
2025-11-10
2025-11-11
2025-11-12
2025-11-13
2025-11-14
2025-11-15
2025-11-16
2025-11-17
2025-11-18
2025-11-19
2025-11-20
2025-11-21
2025-11-22
2025-11-23
2025-11-24
2025-11-25
2025-11-26
2025-11-27
2025-11-28
2025-11-29
2025-11-30
2025-12-01
2025-12-02
2025-12-03
2025-12-04
2025-12-05
2025-12-06
2025-12-07
2025-12-08
2025-12-09
2025-12-10
2025-12-11
2025-12-12
2025-12-13
2025-12-14
2025-12-15
2025-12-16
2025-12-17
2025-12-18
2025-12-19
2025-12-20
2025-12-21
2025-12-22
2025-12-23
2025-12-24
2025-12-25
2025-12-26
2025-12-27
2025-12-28
2025-12-29
2025-12-30
2025-12-31
2026-01-01
2026-01-02
2026-01-03
2026-01-04
2026-01-05
2026-01-06
2026-01-07
2026-01-08
2026-01-09
2026-01-10
2026-01-11
2026-01-12
2026-01-13
2026-01-14
2026-01-15
2026-01-16
2026-01-17
2026-01-18
2026-01-19
2026-01-20
2026-01-21
2026-01-22
2026-01-23
2026-01-24
2026-01-25
2026-01-26
2026-01-27
2026-01-28
2026-01-29
2026-01-30
2026-01-31
2026-02-01
2026-02-02
2026-02-03
2026-02-04
2026-02-05
2026-02-06
2026-02-07
2026-02-08
2026-02-09
2026-02-10
2026-02-11
2026-02-12
2026-02-13
2026-02-14
2026-02-15
2026-02-16
2026-02-17
2026-02-18
2026-02-19
2026-02-20
2026-02-21
2026-02-22
2026-02-23
2026-02-24
2026-02-25
2026-02-26
2026-02-27
2026-02-28
2026-03-01
2026-03-02
2026-03-03
2026-03-04
2026-03-05
2026-03-06
2026-03-07
2026-03-08
2026-03-09
2026-03-10
2026-03-11
2026-03-12
2026-03-13
2026-03-14
2026-03-15
2026-03-16
2026-03-17
2026-03-18
2026-03-19
2026-03-20
2026-03-21
2026-03-22
2026-03-23
2026-03-24
2026-03-25
2026-03-26
2026-03-27
2026-03-28
2026-03-29
2026-03-30
2026-03-31
2026-04-01
2026-04-02
2026-04-03
2026-04-04
2026-04-05
2026-04-06
2026-04-07
2026-04-08
2026-04-09
2026-04-10
2026-04-11
2026-04-12
2026-04-13
2026-04-14
2026-04-15
2026-04-16
2026-04-17
2026-04-18
2026-04-19
2026-04-20
2026-04-21
2026-04-22
2026-04-23
2026-04-24
2026-04-25
2026-04-26
2026-04-27
2026-04-28
2026-04-29
2026-04-30
2026-05-01
2026-05-02
2026-05-03
2026-05-04
2026-05-05
2026-05-06
2026-05-07
2026-05-08
2026-05-09
2026-05-10
2026-05-11
2026-05-12
2026-05-13
2026-05-14
2026-05-15
2026-05-16
2026-05-17
2026-05-18
2026-05-19
2026-05-20
2026-05-21
2026-05-22
2026-05-23
2026-05-24
2026-05-25
2026-05-26
2026-05-27
2026-05-28
2026-05-29
2026-05-30
2026-05-31
2026-06-01
2026-06-02
2026-06-03
2026-06-04
2026-06-05
2026-06-06
2026-06-07
2026-06-08
2026-06-09
2026-06-10
2026-06-11
2026-06-12
2026-06-13
2026-06-14
2026-06-15
2026-06-16
2026-06-17
2026-06-18
2026-06-19
2026-06-20
2026-06-21
2026-06-22
2026-06-23
2026-06-24
2026-06-25
2026-06-26
2026-06-27
2026-06-28
2026-06-29
2026-06-30
2026-07-01
2026-07-02
2026-07-03
2026-07-04
2026-07-05
2026-07-06
2026-07-07
2026-07-08
2026-07-09
2026-07-10
2026-07-11
2026-07-12
2026-07-13
2026-07-14
2026-07-15
2026-07-16
2026-07-17
2026-07-18
2026-07-19
2026-07-20
2026-07-21
2026-07-22
2026-07-23
2026-07-24
2026-07-25
2026-07-26
2026-07-27
2026-07-28
2026-07-29
2026-07-30
2026-07-31
2026-08-01
2026-08-02
2026-08-03
2026-08-04
2026-08-05
2026-08-06
2026-08-07
2026-08-08
2026-08-09
2026-08-10
2026-08-11
2026-08-12
2026-08-13
2026-08-14
2026-08-15
2026-08-16
2026-08-17
2026-08-18
2026-08-19
2026-08-20
2026-08-21
2026-08-22
2026-08-23
2026-08-24
2026-08-25
2026-08-26
2026-08-27
2026-08-28
2026-08-29
2026-08-30
2026-08-31
2026-09-01
2026-09-02
2026-09-03
2026-09-04
2026-09-05
2026-09-06
2026-09-07
2026-09-08
2026-09-09
2026-09-10
2026-09-11
2026-09-12
2026-09-13
2026-09-14
2026-09-15
2026-09-16
2026-09-17
2026-09-18
2026-09-19
2026-09-20
2026-09-21
2026-09-22
2026-09-23
2026-09-24
2026-09-25
2026-09-26
2026-09-27
2026-09-28
2026-09-29
2026-09-30
2026-10-01
2026-10-02
2026-10-03
2026-10-04
2026-10-05
2026-10-06
2026-10-07
2026-10-08
2026-10-09
2026-10-10
2026-10-11
2026-10-12
2026-10-13
2026-10-14
2026-10-15
2026-10-16
2026-10-17
2026-10-18
2026-10-19
2026-10-20
2026-10-21
2026-10-22
2026-10-23
2026-10-24
2026-10-25
2026-10-26
2026-10-27
2026-10-28
2026-10-29
2026-10-30
2026-10-31
2026-11-01
2026-11-02
2026-11-03
2026-11-04
2026-11-05
2026-11-06
2026-11-07
2026-11-08
2026-11-09
2026-11-10
2026-11-11
2026-11-12
2026-11-13
2026-11-14
2026-11-15
2026-11-16
2026-11-17
2026-11-18
2026-11-19
2026-11-20
2026-11-21
2026-11-22
2026-11-23
2026-11-24
2026-11-25
2026-11-26
2026-11-27
2026-11-28
2026-11-29
2026-11-30
2026-12-01
2026-12-02
2026-12-03
2026-12-04
2026-12-05
2026-12-06
2026-12-07
2026-12-08
2026-12-09
2026-12-10
2026-12-11
2026-12-12
2026-12-13
2026-12-14
2026-12-15
2026-12-16
2026-12-17
2026-12-18
2026-12-19
2026-12-20
2026-12-21
2026-12-22
2026-12-23
2026-12-24
2026-12-25
2026-12-26
2026-12-27
2026-12-28
2026-12-29
2026-12-30
2026-12-31
2027-01-01
2027-01-02
2027-01-03
2027-01-04
2027-01-05
2027-01-06
2027-01-07
2027-01-08
2027-01-09
2027-01-10
2027-01-11
2027-01-12
2027-01-13
2027-01-14
2027-01-15
2027-01-16
2027-01-17
2027-01-18
2027-01-19
2027-01-20
2027-01-21
2027-01-22
2027-01-23
2027-01-24
2027-01-25
2027-01-26
2027-01-27
2027-01-28
2027-01-29
2027-01-30
2027-01-31
2027-02-01
2027-02-02
2027-02-03
2027-02-04
2027-02-05
2027-02-06
2027-02-07
2027-02-08
2027-02-09
2027-02-10
2027-02-11
2027-02-12
2027-02-13
2027-02-14
2027-02-15
2027-02-16
2027-02-17
2027-02-18
2027-02-19
2027-02-20
2027-02-21
2027-02-22
2027-02-23
2027-02-24
2027-02-25
2027-02-26
2027-02-27
2027-02-28
2027-03-01
2027-03-02
2027-03-03
2027-03-04
2027-03-05
2027-03-06
2027-03-07
2027-03-08
2027-03-09
2027-03-10
2027-03-11
2027-03-12
2027-03-13
2027-03-14
2027-03-15
2027-03-16
2027-03-17
2027-03-18
2027-03-19
2027-03-20
2027-03-21
2027-03-22
2027-03-23
2027-03-24
2027-03-25
2027-03-26
2027-03-27
2027-03-28
2027-03-29
2027-03-30
2027-03-31
2027-04-01
2027-04-02
2027-04-03
2027-04-04
2027-04-05
2027-04-06
2027-04-07
2027-04-08
2027-04-09
2027-04-10
2027-04-11
2027-04-12
2027-04-13
2027-04-14
2027-04-15
2027-04-16
2027-04-17
2027-04-18
2027-04-19
2027-04-20
2027-04-21
2027-04-22
2027-04-23
2027-04-24
2027-04-25
2027-04-26
2027-04-27
2027-04-28
2027-04-29
2027-04-30
2027-05-01
2027-05-02
2027-05-03
2027-05-04
2027-05-05
2027-05-06
2027-05-07
2027-05-08
2027-05-09
2027-05-10
2027-05-11
2027-05-12
2027-05-13
2027-05-14
2027-05-15
2027-05-16
2027-05-17
2027-05-18
2027-05-19
2027-05-20
2027-05-21
2027-05-22
2027-05-23
2027-05-24
2027-05-25
2027-05-26
2027-05-27
2027-05-28
2027-05-29
2027-05-30
2027-05-31
2027-06-01
2027-06-02
2027-06-03
2027-06-04
2027-06-05
2027-06-06
2027-06-07
2027-06-08
2027-06-09
2027-06-10
2027-06-11
2027-06-12
2027-06-13
2027-06-14
2027-06-15
2027-06-16
2027-06-17
2027-06-18
2027-06-19
2027-06-20
2027-06-21
2027-06-22
2027-06-23
2027-06-24
2027-06-25
2027-06-26
2027-06-27
2027-06-28
2027-06-29
2027-06-30
2027-07-01
2027-07-02
2027-07-03
2027-07-04
2027-07-05
2027-07-06
2027-07-07
2027-07-08
2027-07-09
2027-07-10
2027-07-11
2027-07-12
2027-07-13
2027-07-14
2027-07-15
2027-07-16
2027-07-17
2027-07-18
2027-07-19
2027-07-20
2027-07-21
2027-07-22
2027-07-23
2027-07-24
2027-07-25
2027-07-26
2027-07-27
2027-07-28
2027-07-29
2027-07-30
2027-07-31
2027-08-01
2027-08-02
2027-08-03
2027-08-04
2027-08-05
2027-08-06
2027-08-07
2027-08-08
2027-08-09
2027-08-10
2027-08-11
2027-08-12
2027-08-13
2027-08-14
2027-08-15
2027-08-16
2027-08-17
2027-08-18
2027-08-19
2027-08-20
2027-08-21
2027-08-22
2027-08-23
2027-08-24
2027-08-25
2027-08-26
2027-08-27
2027-08-28
2027-08-29
2027-08-30
2027-08-31
2027-09-01
2027-09-02
2027-09-03
2027-09-04
2027-09-05
2027-09-06
2027-09-07
2027-09-08
2027-09-09
2027-09-10
2027-09-11
2027-09-12
2027-09-13
2027-09-14
2027-09-15
2027-09-16
2027-09-17
2027-09-18
2027-09-19
2027-09-20
2027-09-21
2027-09-22
2027-09-23
2027-09-24
2027-09-25
2027-09-26
2027-09-27
2027-09-28
2027-09-29
2027-09-30
2027-10-01
2027-10-02
2027-10-03
2027-10-04
2027-10-05
2027-10-06
2027-10-07
2027-10-08
2027-10-09
2027-10-10
2027-10-11
2027-10-12
2027-10-13
2027-10-14
2027-10-15
2027-10-16
2027-10-17
2027-10-18
2027-10-19
2027-10-20
2027-10-21
2027-10-22
2027-10-23
2027-10-24
2027-10-25
2027-10-26
2027-10-27
2027-10-28
2027-10-29
2027-10-30
2027-10-31
2027-11-01
2027-11-02
2027-11-03
2027-11-04
2027-11-05
2027-11-06
2027-11-07
2027-11-08
2027-11-09
2027-11-10
2027-11-11
2027-11-12
2027-11-13
2027-11-14
2027-11-15
2027-11-16
2027-11-17
2027-11-18
2027-11-19
2027-11-20
2027-11-21
2027-11-22
2027-11-23
2027-11-24
2027-11-25
2027-11-26
2027-11-27
2027-11-28
2027-11-29
2027-11-30
2027-12-01
2027-12-02
2027-12-03
2027-12-04
2027-12-05
2027-12-06
2027-12-07
2027-12-08
2027-12-09
2027-12-10
2027-12-11
2027-12-12
2027-12-13
2027-12-14
2027-12-15
2027-12-16
2027-12-17
2027-12-18
2027-12-19
2027-12-20
2027-12-21
2027-12-22
2027-12-23
2027-12-24
2027-12-25
2027-12-26
2027-12-27
2027-12-28
2027-12-29
2027-12-30
2027-12-31
2028-01-01
2028-01-02
2028-01-03
2028-01-04
2028-01-05
2028-01-06
2028-01-07
2028-01-08
2028-01-09
2028-01-10
2028-01-11
2028-01-12
2028-01-13
2028-01-14
2028-01-15
2028-01-16
2028-01-17
2028-01-18
2028-01-19
2028-01-20
2028-01-21
2028-01-22
2028-01-23
2028-01-24
2028-01-25
2028-01-26
2028-01-27
2028-01-28
2028-01-29
2028-01-30
2028-01-31
2028-02-01
2028-02-02
2028-02-03
2028-02-04
2028-02-05
2028-02-06
2028-02-07
2028-02-08
2028-02-09
2028-02-10
2028-02-11
2028-02-12
2028-02-13
2028-02-14
2028-02-15
2028-02-16
2028-02-17
2028-02-18
2028-02-19
2028-02-20
2028-02-21
2028-02-22
2028-02-23
2028-02-24
2028-02-25
2028-02-26
2028-02-27
2028-02-28
2028-02-29
2028-03-01
2028-03-02
2028-03-03
2028-03-04
2028-03-05
2028-03-06
2028-03-07
2028-03-08
2028-03-09
2028-03-10
2028-03-11
2028-03-12
2028-03-13
2028-03-14
2028-03-15
2028-03-16
2028-03-17
2028-03-18
2028-03-19
2028-03-20
2028-03-21
2028-03-22
2028-03-23
2028-03-24
2028-03-25
2028-03-26
2028-03-27
2028-03-28
2028-03-29
2028-03-30
2028-03-31
2028-04-01
2028-04-02
2028-04-03
2028-04-04
2028-04-05
2028-04-06
2028-04-07
2028-04-08
2028-04-09
2028-04-10
2028-04-11
2028-04-12
2028-04-13
2028-04-14
2028-04-15
2028-04-16
2028-04-17
2028-04-18
2028-04-19
2028-04-20
2028-04-21
2028-04-22
2028-04-23
2028-04-24
2028-04-25
2028-04-26
2028-04-27
2028-04-28
2028-04-29
2028-04-30
2028-05-01
2028-05-02
2028-05-03
2028-05-04
2028-05-05
2028-05-06
2028-05-07
2028-05-08
2028-05-09
2028-05-10
2028-05-11
2028-05-12
2028-05-13
2028-05-14
2028-05-15
2028-05-16
2028-05-17
2028-05-18
2028-05-19
2028-05-20
2028-05-21
2028-05-22
2028-05-23
2028-05-24
2028-05-25
2028-05-26
2028-05-27
2028-05-28
2028-05-29
2028-05-30
2028-05-31
2028-06-01
2028-06-02
2028-06-03
2028-06-04
2028-06-05
2028-06-06
2028-06-07
2028-06-08
2028-06-09
2028-06-10
2028-06-11
2028-06-12
2028-06-13
2028-06-14
2028-06-15
2028-06-16
2028-06-17
2028-06-18
2028-06-19
2028-06-20
2028-06-21
2028-06-22
2028-06-23
2028-06-24
2028-06-25
2028-06-26
2028-06-27
2028-06-28
2028-06-29
2028-06-30
2028-07-01
2028-07-02
2028-07-03
2028-07-04
2028-07-05
2028-07-06
2028-07-07
2028-07-08
2028-07-09
2028-07-10
2028-07-11
2028-07-12
2028-07-13
2028-07-14
2028-07-15
2028-07-16
2028-07-17
2028-07-18
2028-07-19
2028-07-20
2028-07-21
2028-07-22
2028-07-23
2028-07-24
2028-07-25
2028-07-26
2028-07-27
2028-07-28
2028-07-29
2028-07-30
2028-07-31
2028-08-01
2028-08-02
2028-08-03
2028-08-04
2028-08-05
2028-08-06
2028-08-07
2028-08-08
2028-08-09
2028-08-10
2028-08-11
2028-08-12
2028-08-13
2028-08-14
2028-08-15
2028-08-16
2028-08-17
2028-08-18
2028-08-19
2028-08-20
2028-08-21
2028-08-22
2028-08-23
2028-08-24
2028-08-25
2028-08-26
2028-08-27
2028-08-28
2028-08-29
2028-08-30
2028-08-31
2028-09-01
2028-09-02
2028-09-03
2028-09-04
2028-09-05
2028-09-06
2028-09-07
2028-09-08
2028-09-09
2028-09-10
2028-09-11
2028-09-12
2028-09-13
2028-09-14
2028-09-15
2028-09-16
2028-09-17
2028-09-18
2028-09-19
2028-09-20
2028-09-21
2028-09-22
2028-09-23
2028-09-24
2028-09-25
2028-09-26
2028-09-27
2028-09-28
2028-09-29
2028-09-30
2028-10-01
2028-10-02
2028-10-03
2028-10-04
2028-10-05
2028-10-06
2028-10-07
2028-10-08
2028-10-09
2028-10-10
2028-10-11
2028-10-12
2028-10-13
2028-10-14
2028-10-15
2028-10-16
2028-10-17
2028-10-18
2028-10-19
2028-10-20
2028-10-21
2028-10-22
2028-10-23
2028-10-24
2028-10-25
2028-10-26
2028-10-27
2028-10-28
2028-10-29
2028-10-30
2028-10-31
2028-11-01
2028-11-02
2028-11-03
2028-11-04
2028-11-05
2028-11-06
2028-11-07
2028-11-08
2028-11-09
2028-11-10
2028-11-11
2028-11-12
2028-11-13
2028-11-14
2028-11-15
2028-11-16
2028-11-17
2028-11-18
2028-11-19
2028-11-20
2028-11-21
2028-11-22
2028-11-23
2028-11-24
2028-11-25
2028-11-26
2028-11-27
2028-11-28
2028-11-29
2028-11-30
2028-12-01
2028-12-02
2028-12-03
2028-12-04
2028-12-05
2028-12-06
2028-12-07
2028-12-08
2028-12-09
2028-12-10
2028-12-11
2028-12-12
2028-12-13
2028-12-14
2028-12-15
2028-12-16
2028-12-17
2028-12-18
2028-12-19
2028-12-20
2028-12-21
2028-12-22
2028-12-23
2028-12-24
2028-12-25
2028-12-26
2028-12-27
2028-12-28
2028-12-29
2028-12-30
2028-12-31
2029-01-01
2029-01-02
2029-01-03
2029-01-04
2029-01-05
2029-01-06
2029-01-07
2029-01-08
2029-01-09
2029-01-10
2029-01-11
2029-01-12
2029-01-13
2029-01-14
2029-01-15
2029-01-16
2029-01-17
2029-01-18
2029-01-19
2029-01-20
2029-01-21
2029-01-22
2029-01-23
2029-01-24
2029-01-25
2029-01-26
2029-01-27
2029-01-28
2029-01-29
2029-01-30
2029-01-31
2029-02-01
2029-02-02
2029-02-03
2029-02-04
2029-02-05
2029-02-06
2029-02-07
2029-02-08
2029-02-09
2029-02-10
2029-02-11
2029-02-12
2029-02-13
2029-02-14
2029-02-15
2029-02-16
2029-02-17
2029-02-18
2029-02-19
2029-02-20
2029-02-21
2029-02-22
2029-02-23
2029-02-24
2029-02-25
2029-02-26
2029-02-27
2029-02-28
2029-03-01
2029-03-02
2029-03-03
2029-03-04
2029-03-05
2029-03-06
2029-03-07
2029-03-08
2029-03-09
2029-03-10
2029-03-11
2029-03-12
2029-03-13
2029-03-14
2029-03-15
2029-03-16
2029-03-17
2029-03-18
2029-03-19
2029-03-20
2029-03-21
2029-03-22
2029-03-23
2029-03-24
2029-03-25
2029-03-26
2029-03-27
2029-03-28
2029-03-29
2029-03-30
2029-03-31
2029-04-01
2029-04-02
2029-04-03
2029-04-04
2029-04-05
2029-04-06
2029-04-07
2029-04-08
2029-04-09
2029-04-10
2029-04-11
2029-04-12
2029-04-13
2029-04-14
2029-04-15
2029-04-16
2029-04-17
2029-04-18
2029-04-19
2029-04-20
2029-04-21
2029-04-22
2029-04-23
2029-04-24
2029-04-25
2029-04-26
2029-04-27
2029-04-28
2029-04-29
2029-04-30
2029-05-01
2029-05-02
2029-05-03
2029-05-04
2029-05-05
2029-05-06
2029-05-07
2029-05-08
2029-05-09
2029-05-10
2029-05-11
2029-05-12
2029-05-13
2029-05-14
2029-05-15
2029-05-16
2029-05-17
2029-05-18
2029-05-19
2029-05-20
2029-05-21
2029-05-22
2029-05-23
2029-05-24
2029-05-25
2029-05-26
2029-05-27
2029-05-28
2029-05-29
2029-05-30
2029-05-31
2029-06-01
2029-06-02
2029-06-03
2029-06-04
2029-06-05
2029-06-06
2029-06-07
2029-06-08
2029-06-09
2029-06-10
2029-06-11
2029-06-12
2029-06-13
2029-06-14
2029-06-15
2029-06-16
2029-06-17
2029-06-18
2029-06-19
2029-06-20
2029-06-21
2029-06-22
2029-06-23
2029-06-24
2029-06-25
2029-06-26
2029-06-27
2029-06-28
2029-06-29
2029-06-30
2029-07-01
2029-07-02
2029-07-03
2029-07-04
2029-07-05
2029-07-06
2029-07-07
2029-07-08
2029-07-09
2029-07-10
2029-07-11
2029-07-12
2029-07-13
2029-07-14
2029-07-15
2029-07-16
2029-07-17
2029-07-18
2029-07-19
2029-07-20
2029-07-21
2029-07-22
2029-07-23
2029-07-24
2029-07-25
2029-07-26
2029-07-27
2029-07-28
2029-07-29
2029-07-30
2029-07-31
2029-08-01
2029-08-02
2029-08-03
2029-08-04
2029-08-05
2029-08-06
2029-08-07
2029-08-08
2029-08-09
2029-08-10
2029-08-11
2029-08-12
2029-08-13
2029-08-14
2029-08-15
2029-08-16
2029-08-17
2029-08-18
2029-08-19
2029-08-20
2029-08-21
2029-08-22
2029-08-23
2029-08-24
2029-08-25
2029-08-26
2029-08-27
2029-08-28
2029-08-29
2029-08-30
2029-08-31
2029-09-01
2029-09-02
2029-09-03
2029-09-04
2029-09-05
2029-09-06
2029-09-07
2029-09-08
2029-09-09
2029-09-10
2029-09-11
2029-09-12
2029-09-13
2029-09-14
2029-09-15
2029-09-16
2029-09-17
2029-09-18
2029-09-19
2029-09-20
2029-09-21
2029-09-22
2029-09-23
2029-09-24
2029-09-25
2029-09-26
2029-09-27
2029-09-28
2029-09-29
2029-09-30
2029-10-01
2029-10-02
2029-10-03
2029-10-04
2029-10-05
2029-10-06
2029-10-07
2029-10-08
2029-10-09
2029-10-10
2029-10-11
2029-10-12
2029-10-13
2029-10-14
2029-10-15
2029-10-16
2029-10-17
2029-10-18
2029-10-19
2029-10-20
2029-10-21
2029-10-22
2029-10-23
2029-10-24
2029-10-25
2029-10-26
2029-10-27
2029-10-28
2029-10-29
2029-10-30
2029-10-31
2029-11-01
2029-11-02
2029-11-03
2029-11-04
2029-11-05
2029-11-06
2029-11-07
2029-11-08
2029-11-09
2029-11-10
2029-11-11
2029-11-12
2029-11-13
2029-11-14
2029-11-15
2029-11-16
2029-11-17
2029-11-18
2029-11-19
2029-11-20
2029-11-21
2029-11-22
2029-11-23
2029-11-24
2029-11-25
2029-11-26
2029-11-27
2029-11-28
2029-11-29
2029-11-30
2029-12-01
2029-12-02
2029-12-03
2029-12-04
2029-12-05
2029-12-06
2029-12-07
2029-12-08
2029-12-09
2029-12-10
2029-12-11
2029-12-12
2029-12-13
2029-12-14
2029-12-15
2029-12-16
2029-12-17
2029-12-18
2029-12-19
2029-12-20
2029-12-21
2029-12-22
2029-12-23
2029-12-24
2029-12-25
2029-12-26
2029-12-27
2029-12-28
2029-12-29
2029-12-30
2029-12-31
2030-01-01
2030-01-02
2030-01-03
2030-01-04
2030-01-05
2030-01-06
2030-01-07
2030-01-08
2030-01-09
2030-01-10
2030-01-11
2030-01-12
2030-01-13
2030-01-14
2030-01-15
2030-01-16
2030-01-17
2030-01-18
2030-01-19
2030-01-20
2030-01-21
2030-01-22
2030-01-23
2030-01-24
2030-01-25
2030-01-26
2030-01-27
2030-01-28
2030-01-29
2030-01-30
2030-01-31
2030-02-01
2030-02-02
2030-02-03
2030-02-04
2030-02-05
2030-02-06
2030-02-07
2030-02-08
2030-02-09
2030-02-10
2030-02-11
2030-02-12
2030-02-13
2030-02-14
2030-02-15
2030-02-16
2030-02-17
2030-02-18
2030-02-19
2030-02-20
2030-02-21
2030-02-22
2030-02-23
2030-02-24
2030-02-25
2030-02-26
2030-02-27
2030-02-28
2030-03-01
2030-03-02
2030-03-03
2030-03-04
2030-03-05
2030-03-06
2030-03-07
2030-03-08
2030-03-09
2030-03-10
2030-03-11
2030-03-12
2030-03-13
2030-03-14
2030-03-15
2030-03-16
2030-03-17
2030-03-18
2030-03-19
2030-03-20
2030-03-21
2030-03-22
2030-03-23
2030-03-24
2030-03-25
2030-03-26
2030-03-27
2030-03-28
2030-03-29
2030-03-30
2030-03-31
2030-04-01
2030-04-02
2030-04-03
2030-04-04
2030-04-05
2030-04-06
2030-04-07
2030-04-08
2030-04-09
2030-04-10
2030-04-11
2030-04-12
2030-04-13
2030-04-14
2030-04-15
2030-04-16
2030-04-17
2030-04-18
2030-04-19
2030-04-20
2030-04-21
2030-04-22
2030-04-23
2030-04-24
2030-04-25
2030-04-26
2030-04-27
2030-04-28
2030-04-29
2030-04-30
2030-05-01
2030-05-02
2030-05-03
2030-05-04
2030-05-05
2030-05-06
2030-05-07
2030-05-08
2030-05-09
2030-05-10
2030-05-11
2030-05-12
2030-05-13
2030-05-14
2030-05-15
2030-05-16
2030-05-17
2030-05-18
2030-05-19
2030-05-20
2030-05-21
2030-05-22
2030-05-23
2030-05-24
2030-05-25
2030-05-26
2030-05-27
2030-05-28
2030-05-29
2030-05-30
2030-05-31
2030-06-01
2030-06-02
2030-06-03
2030-06-04
2030-06-05
2030-06-06
2030-06-07
2030-06-08
2030-06-09
2030-06-10
2030-06-11
2030-06-12
2030-06-13
2030-06-14
2030-06-15
2030-06-16
2030-06-17
2030-06-18
2030-06-19
2030-06-20
2030-06-21
2030-06-22
2030-06-23
2030-06-24
2030-06-25
2030-06-26
2030-06-27
2030-06-28
2030-06-29
2030-06-30
2030-07-01
2030-07-02
2030-07-03
2030-07-04
2030-07-05
2030-07-06
2030-07-07
2030-07-08
2030-07-09
2030-07-10
2030-07-11
2030-07-12
2030-07-13
2030-07-14
2030-07-15
2030-07-16
2030-07-17
2030-07-18
2030-07-19
2030-07-20
2030-07-21
2030-07-22
2030-07-23
2030-07-24
2030-07-25
2030-07-26
2030-07-27
2030-07-28
2030-07-29
2030-07-30
2030-07-31
2030-08-01
2030-08-02
2030-08-03
2030-08-04
2030-08-05
2030-08-06
2030-08-07
2030-08-08
2030-08-09
2030-08-10
2030-08-11
2030-08-12
2030-08-13
2030-08-14
2030-08-15
2030-08-16
2030-08-17
2030-08-18
2030-08-19
2030-08-20
2030-08-21
2030-08-22
2030-08-23
2030-08-24
2030-08-25
2030-08-26
2030-08-27
2030-08-28
2030-08-29
2030-08-30
2030-08-31
2030-09-01
2030-09-02
2030-09-03
2030-09-04
2030-09-05
2030-09-06
2030-09-07
2030-09-08
2030-09-09
2030-09-10
2030-09-11
2030-09-12
2030-09-13
2030-09-14
2030-09-15
2030-09-16
2030-09-17
2030-09-18
2030-09-19
2030-09-20
2030-09-21
2030-09-22
2030-09-23
2030-09-24
2030-09-25
2030-09-26
2030-09-27
2030-09-28
2030-09-29
2030-09-30
2030-10-01
2030-10-02
2030-10-03
2030-10-04
2030-10-05
2030-10-06
2030-10-07
2030-10-08
2030-10-09
2030-10-10
2030-10-11
2030-10-12
2030-10-13
2030-10-14
2030-10-15
2030-10-16
2030-10-17
2030-10-18
2030-10-19
2030-10-20
2030-10-21
2030-10-22
2030-10-23
2030-10-24
2030-10-25
2030-10-26
2030-10-27
2030-10-28
2030-10-29
2030-10-30
2030-10-31
2030-11-01
2030-11-02
2030-11-03
2030-11-04
2030-11-05
2030-11-06
2030-11-07
2030-11-08
2030-11-09
2030-11-10
2030-11-11
2030-11-12
2030-11-13
2030-11-14
2030-11-15
2030-11-16
2030-11-17
2030-11-18
2030-11-19
2030-11-20
2030-11-21
2030-11-22
2030-11-23
2030-11-24
2030-11-25
2030-11-26
2030-11-27
2030-11-28
2030-11-29
2030-11-30
2030-12-01
2030-12-02
2030-12-03
2030-12-04
2030-12-05
2030-12-06
2030-12-07
2030-12-08
2030-12-09
2030-12-10
2030-12-11
2030-12-12
2030-12-13
2030-12-14
2030-12-15
2030-12-16
2030-12-17
2030-12-18
2030-12-19
2030-12-20
2030-12-21
2030-12-22
2030-12-23
2030-12-24
2030-12-25
2030-12-26
2030-12-27
2030-12-28
2030-12-29
2030-12-30
2030-12-31

## Safety Induction (hidden)
Date | Overall Induction Done | Report No
2021-01-01 | 280
2021-02-01 | 290
2021-03-01 | 160
2021-04-01 | 180
2021-05-01 | 190
2021-06-01 | 140
2021-07-01 | 110
2021-08-01 | 110

## EHS Awarness Program (hidden)
Date | EHS Awarness Program | Report No
2021-01-01 | 4
2021-02-01 | 6
2021-03-01 | 6
2021-04-01 | 3
2021-05-01 | 2
2021-06-01 | 5
2021-07-01 | 2
2021-08-01 | 3

## Tool Box Kit (hidden)
Date | Tool Box Kit | Report No
2021-01-01 | 4
2021-02-01 | 6
2021-03-01 | 6
2021-04-01 | 3
2021-05-01 | 2
2021-06-01 | 5
2021-07-01 | 2
2021-08-01 | 3

## Safety NCR Raised
Date | Cumulative HSE NCR as on date Issued | Cumulative HSE NCR as on date Open | NCR Issued This Week | NCR Pending This Week | NCR Closed This Week | Remarks | Report No
2021-09-24 | 39 | 3 | 2 | 3 | 2 |  | 19
2021-10-01 | 39 | 3 | 0 | 0 | 0 |  | 20
2021-10-08 | 39 | 0 | 0 | 0 | 0 |  | 21
2021-10-15 | 39 | 0 | 0 | 0 | 0 |  | 22
2021-10-22 | 39 | 0 | 0 | 0 | 0 |  | 23
2021-10-29 | 39 | 0 | 0 | 0 | 0 |  | 24
2021-11-08 | 39 | 0 | 0 | 0 | 0 |  | 25
2021-11-19 | 39 | 0 | 0 | 0 | 0 |  | 26
2021-10-26 | 39 | 0 | 0 | 0 | 0 |  | 27
2021-03-12 | 42 | 0 | 42 | 0 | 0 |  | 28
2021-10-12 | 43 | 1 | 1 | 1 | 0 |  | 29
Formulas:
Date = [Date, row above]+7

## Safety Observ Cum - Gleeds
Date | Cum Open | Cum Issued | Cum Closed | Report No
2021-12-03 | 0 | 10 | 10 | 28
2021-12-10 | 25 | 25 | 0 | 29

## Safety Observ - Gleeds
Date | Open | Issued | Closed | Report No
2021-12-03 | 0 | 10 | 10 | 28
2021-12-10 | 25 | 25 | 0 | 29

## Work Permit Status (hidden)
Date | Issued | Violated | Report No
2021-01-01 | 4 | 1
2021-02-01 | 6 | 2
2021-03-01 | 6 | 3
2021-04-01 | 3 | 4
2021-05-01 | 2 | 5
2021-06-01 | 5 | 6
2021-07-01 | 2 | 7
2021-08-01 | 3 | 8
1

## Near Miss Vs Minor vs Major Inj (hidden)
Date | Near Misses | Minor Injury | Major Injury | Report No
2021-10-01 | 4 | 1 | 2 | 1
2021-02-01 | 6 | 2 | 2 | 2
2021-03-01 | 6 | 3 | 2 | 3
2021-04-01 | 3 | 4 | 1 | 4
2021-05-01 | 2 | 5 | 1 | 5
2021-06-01 | 5 | 6 | 2 | 6
2021-07-01 | 2 | 7 | 1 | 7
2021-08-01 | 3 | 8 | 1 | 8
|  | 1 |  | 9

## Total No's of Audits Conducted (hidden)
Date | Audits no | Report No
2021-01-01 | 4 | 1
2021-02-01 | 6 | 2
2021-03-01 | 6 | 3
2021-04-01 | 3 | 4
2021-05-01 | 2 | 5
2021-06-01 | 5 | 6
2021-07-01 | 2 | 7
2021-08-01 | 3 | 8

## Safety Non Compliance Report
Date | CUMMUNLATIVE RAISED | CUMMULATIVE CLOSED | CUMMULATIVE OPEN | RAISED THIS WEEK | CLOSED THIS WEEK | OPEN THIS WEEK | Remarks | Report No
2021-09-24 | 1999 | 1980 | 19 | 53 | 45 | 20 |  | 19
2021-10-01 | 2090 | 2038 | 52 | 91 | 59 | 52 |  | 20
2021-10-08 | 2160 | 2143 | 17 | 70 | 105 | 17 |  | 21
2021-10-15 | 2190 | 2183 | 7 | 30 | 23 | 7 |  | 22
2021-10-22 | 2232 | 2220 | 12 | 42 | 35 | 7 |  | 23
2021-10-29 | 2279 | 2265 | 14 | 47 | 47 | 0 |  | 24
2021-11-08 | 2335 | 2282 | 53 | 72 | 64 | 8 |  | 25
2021-11-19 | 2415 | 2282 | 61 | 80 | 72 | 8 |  | 26
2021-10-26 | 2695 | 2647 | 48 | 109 | 75 | 34 |  | 27
2021-03-12 | 2670 | 2650 | 20 | 84 | 64 | 20 |  | 28
2021-10-12 | 2763 | 2745 | 18 | 93 | 108 | 18 |  | 29

## Safety Non Complianc-Contractor
Date | Contractor Name | No of Non Compliance | Remarks | Report No
2021-09-24 | YY | 0 |  | 19
2021-09-24 | TT | 0 |  | 19
2021-09-24 | EE | 6 |  | 19
2021-09-24 | XX | 46 |  | 19
2021-09-24 | AA | 0 |  | 19
2021-10-01 | YY | 0 |  | 20
2021-10-01 | TT | 0 |  | 20
2021-10-01 | EE | 4 |  | 20
2021-10-01 | XX | 87 |  | 20
2021-10-01 | AA | 0 |  | 20
2021-10-08 | YY | 0 |  | 21
2021-10-08 | TT | 0 |  | 21
2021-10-08 | EE | 4 |  | 21
2021-10-08 | XX | 87 |  | 21
2021-10-08 | AA | 0 |  | 21
2021-10-15 | YY | 28 |  | 22
2021-10-15 | TT | 1 |  | 22
2021-10-15 | EE | 1 |  | 22
2021-10-22 | AA | 8 |  | 23
2021-10-22 | XX | 32 |  | 23
2021-10-29 | AA | 4 |  | 24
2021-10-29 | XX | 43 |  | 24
2021-11-08 | AA | 3 |  | 25
2021-11-08 | XX | 69 |  | 25
2021-11-19 | AA | 2 |  | 26
2021-11-19 | XX | 77 |  | 26
2021-11-19 | TT | 1 |  | 26
2021-10-26 | AA | 10 |  | 27
2021-10-26 | XX | 99 |  | 27
2021-03-12 | AA | 83 |  | 28
2021-03-12 | XX | 1 |  | 28
2021-10-12 | AA | 4 |  | 29
2021-10-12 | XX | 80 |  | 29
2021-10-12 | TT | 2 |  | 29
2021-10-12 | EE | 6 |  | 29
Formulas:
Date = [Date, row above]

## Total of Loss & No Safe hours (hidden)
Date | No of Loss Time Injuries (LTI) No's | No of Loss Time Accident (LTA) No's | NO of Safe Manhours | Safe Vehicles Running Hours | Report No
2021-01-01 | 4 | 1 | 2 | 2 | 1
2021-02-01 | 6 | 2 | 2 | 2
2021-03-01 | 6 | 3 | 2 | 2
2021-04-01 | 3 | 4 | 1 | 1
2021-05-01 | 2 | 5 | 1 | 1
2021-06-01 | 5 | 6 | 2 | 2
2021-07-01 | 2 | 7 | 1 | 1
2021-08-01 | 3 | 8 | 1 | 1
1

## Risk Assessment
Date | CUMMULATIVE RECEIVED | CUMMULATIVE APPROVED | CUMMULATIVE REVIEW & COMMENTS | RECEIVED THIS WEEK | APPROVED THIS WEEK | REVIEW & COMMENTS THIS WEEK | Remarks | Report No
2021-09-24 | 80 | 80 | 0 | 1 | 2 | 0 |  | 19
2021-10-01 | 80 | 80 | 0 | 0 | 0 | 0 |  | 20
2021-10-08 | 81 | 80 | 1 | 1 | 0 | 1 |  | 21
2021-10-15 | 81 | 80 | 1 | 0 | 0 | 0 |  | 22
2021-10-22 | 83 | 81 | 2 | 2 | 1 | 2 |  | 23
2021-10-29 | 83 | 81 | 2 | 0 | 0 | 0 |  | 24
2021-11-08 | 85 | 84 | 1 | 2 | 1 | 1 |  | 25
2021-11-19 | 85 | 85 | 0 | 0 | 0 | 0 |  | 26
2021-10-26 | 86 | 85 | 0 | 1 | 1 | 0 |  | 27
2021-03-12 | 86 | 86 | 0 | 0 | 1 | 0 |  | 28
2021-10-13 | 89 | 87 | 2 | 3 | 1 | 2 |  | 29
Formulas:
Date = [Date, row above]+7