## Risk Register
S.No | Date | Risk Category | Risk Description | Probability | Impact | Risk Score | Risk owner | Mitigation Strategy | Risk Status
1 | 2021-09-24 | Procurement | Procurement - Façade works | 4 | 5 | 20 | AA | AA must commence the procurement process immediately, since it is a most critical resource to consider as per the baseline schedule
2 | 2021-09-24 | Construction | Main Building - Grid 4 to 8 - Delay in Steel Structure erection & Deck sheet fixing | 5 | 5 | 25 | XX | XX must mobilise the required materials & accelerate the progress to complete as early as possible
3 | 2021-09-24 | Construction | Fireproof painting for columns & beams in 2nd & 3rd floor levels | 4 | 3 | 12 | AA | XX must speed up the progress concurrently in 2nd and 3rd floors by deploying more resources
4 | 2021-09-24 | Construction | Main Building - Deck slab concreting - Terrace floor | 5 | 4 | 20 | All | XX must complete the steel erection & deck sheet fixing as early as possible to complete deck slab concreting. L&W can commence the deck slab concreting for grid 1 to 4
5 | 2021-09-24 | Construction | Main Building - Deck slab concreting - 4th floor to 6th floor | 5 | 4 | 20 | All | AA must deploy more resourecs to perform it concurrently with terrace deck slab to avoid further delay
1 | 2021-12-10 | Construction | Main building - External - Commencement of shaft Civil & MEP works | 4 | 5 | 20 | ACX / L&W | L&W must commence the shaft civil works, wherever the work front is available by deploying more resources concurrently